## README
Nabd — Hospital / Clinic Management System
Implementation Task Plan v2 — rebuilt against the updated wireframe
Prepared for | Harish
Date | 13 August 2026
Supersedes | v1 of 11 August 2026 (202 tasks, 1,210 points)
Source | Nabd wireframe (Platform Console v29 + current shell) and DESIGN.md in the connected folder
WHAT THE UPDATED WIREFRAME CHANGED
The wireframe now carries a formal requirement register — 185 identifiers across 30 prefixes (SYS, PAT, CGV, CAD, RCP, OWN, PKG, BIL,
PHR, CMP, DPO, SSA, SCS, AGG, CEO, NFR, MKT and nine clinical specialties). Every task below is traced to those identifiers, and the
Requirement Coverage tab proves all 185 are covered.
Four product areas exist now that did not exist in v1: the patient WhatsApp surface, caregiver and family handling, the aggregator layer,
and a rebuilt platform console with seven distinct SaaS operator roles.
DESIGN.md gained a full chart system (sections 8.22-8.29) and a messaging component set (8.16-8.21). Both are now build epics.
Scope roughly doubled: 349 tasks and 2,260 points against v1's 202 and 1,210.
EXPLICIT NON-GOALS TAKEN FROM THE WIREFRAME — do not build these
NFR-06 | No SSO and no hardware security keys. Staff sign in with WhatsApp OTP, a short PIN or an authenticator app. The v1 SSO/OIDC task has been deleted.
CAD-10 | No payroll engine. Payroll is a CSV export only.
SYS-10 | No live claims pipeline. Full claims go via certified middleware in Phase 3. Ayushman is out of scope. Only a simple claim export (BIL-11) and NPHIES eligibility-check-lite (RCP-07) are in scope.
PHR-04 | Controlled drugs get a warning and a register entry, never a hard block — no registered pharmacist licence is assumed.
CEO-14 | No review filtering or gating. Nabd and Google ratings are never blended into one number.
CEO-25 | Adherence data is capture-only and is never monetised.
AGG-03 | Word-to-specialty matching only. No symptom interpretation and no clinical triage.
PED-04 | Growth percentiles are never calculated in the UI — only a validated growth service may produce them.
PLANNING ASSUMPTIONS — edit the blue cells; everything derived recalculates
Assumption | Value | Note
Sprint length (weeks) | 2 | Standard two-week iteration
Velocity per squad (points / sprint) | 40 | A squad is roughly 6 people. Sprint capacity = this multiplied by the squads active that sprint.
Person-days per story point | 0.6 | Calibrate after two or three sprints; drives the indicative effort column only.
Blended cost per person-day | 0 | Optional — enter your rate to cost the plan. Left at zero by the author.
Peak squads in parallel | 5 | Reached in sprints 14-18. Roughly 30 delivery people at peak — this scope cannot be absorbed by one team.
TABS
Tab | Purpose
Backlog | The full task list — 349 rows. One row is one epic-level story. Edit Status, Sprint, Points and Owner.
Requirement Coverage | Every one of the 185 wireframe requirement identifiers mapped to the tasks that deliver it. Zero uncovered is the release gate.
Epics | Automatic rollup by epic. All formulas — do not type here.
Sprints | Sprint load against ramped squad capacity. Over-capacity sprints turn red.
Tracks | Rollup by parallel delivery track, showing how the four tracks are staffed.
RBAC Matrix | The clinic role and permission grid taken from the wireframe — the specification for epic E06.
SaaS Operator Roles | The seven platform-side roles from SSA-02 and what each may reach.
Security Controls | Cybersecurity, privacy and compliance controls mapped to delivering tasks, with a go-live gate counter.
Risks | Delivery, security and clinical-safety risks with owners and mitigations.
Changes from v1 | What was added, removed and re-scoped when the wireframe was updated.
Estimates are the author's architectural judgement from the wireframe, not a quotation. They assume no pre-existing codebase.

## Backlog
ID | Epic | Module | Task | Description | Requirement IDs | Roles Impacted | Track | Discipline | Priority | Delivery Phase | Story Points | Sprint | Release Band | Est. Person-Days | Depends On | Acceptance Criteria | Status | Owner / Squad
NB-001 | E01 Foundation & Architecture | Architecture | Define target architecture & ADR set | Modular monolith + Postgres, region-isolated stacks for India and KSA, event bus for messaging. ADRs for datastore, tenancy, hosting. | SYS-14,NFR-04 | All | Shared | Architecture | Must | MVP | 8 | 1 |  |  |  | ADRs approved; C4 L1/L2 published; region topology signed off | Not started
NB-002 | E01 Foundation & Architecture | Architecture | Multi-tenancy isolation model + irreversible region lock | Region is chosen at provisioning and locked permanently. No cross-region replication; region-scoped KMS keys. | SYS-14,NFR-04 | Platform | Shared | Architecture | Must | MVP | 8 | 1 |  |  | NB-001 | PoC proves row-level isolation; region field immutable after provisioning; attempt to change is rejected and audited | Not started
NB-003 | E01 Foundation & Architecture | Data | Core data model & ERD | Tenant, Clinic, Branch, Staff, Role, Patient, FamilyMember, Encounter, Appointment, Invoice, Package, Prescription, PharmacyItem, ConsentRecord, AuditEvent. | SYS-13 | All | Shared | Backend | Must | MVP | 13 | 1 |  |  | NB-001 | ERD reviewed; migrations generated; naming conventions documented | Not started
NB-004 | E01 Foundation & Architecture | Data | Database migration framework & seed data | Versioned reversible migrations; seed tenants for India and KSA demo clinics matching the wireframe fixtures. |  | All | Shared | Backend | Must | MVP | 3 | 2 |  |  | NB-003 | Migrate up/down clean; seeds reproduce wireframe demo data | Not started
NB-005 | E01 Foundation & Architecture | API | API standards, versioning & error contract | REST /v1, RFC7807 errors, pagination, idempotency keys on every financial and clinical write. | SYS-06 | All | Shared | Backend | Must | MVP | 5 | 2 |  |  | NB-001 | OpenAPI published; CI linter enforces the standard | Not started
NB-006 | E01 Foundation & Architecture | API | API gateway & per-role BFF layer | Single entry point; role-shaped payloads so the mobile queue screen stays small. | NFR-02 | All | Shared | Backend | Should | MVP | 5 | 3 |  |  | NB-005 | p95 payload under 150KB on the queue screen | Not started
NB-007 | E01 Foundation & Architecture | Platform | Event bus & transactional outbox | No clinical, billing or messaging event may be lost. Drives WhatsApp, SMS, recall and webhooks. | SYS-01,NFR-12 | All | Shared | Backend | Must | MVP | 8 | 3 |  |  | NB-003, NB-005 | Zero message loss under forced consumer failure | Not started
NB-008 | E01 Foundation & Architecture | Platform | Feature-flag & module-entitlement service | Drives Included / Trial / Paid add-on / Upgrade required / Disabled-by-clinic / Disabled-by-platform states. | SYS-20,CAD-13 | Owner,Platform | Shared | Backend | Must | MVP | 8 | 3 |  |  | NB-001, NB-002 | Entitlement change propagates in under 60s; upgrade/downgrade under 5 minutes with no data loss | Not started
NB-009 | E01 Foundation & Architecture | Platform | Config & secrets management with role separation | Installation secrets are separate from tenant integration secrets — two different operator roles. | SYS-14 | All | Shared | DevOps | Must | MVP | 5 | 2 |  |  | NB-299 | Secret scan clean; installation and tenant secrets held in separate scopes with separate access | Not started
NB-010 | E01 Foundation & Architecture | Data | Reference data service | ICD-10 subset, drug master (India NMC generics + KSA SFDA identifiers), charge catalogue, GST/VAT rate tables, vaccine schedules. | GP-05,DOC-06 | Doctor,Reception | Shared | Backend | Must | MVP | 8 | 4 |  |  | NB-003 | Catalogue seeded; rates and drug lists versioned by effective date | Not started
NB-011 | E01 Foundation & Architecture | Platform | Shared reason-code service | One shared reason list reused by cancellation, reschedule, block, override and refusal flows. | SYS-07 | All | Shared | Backend | Must | MVP | 3 | 4 |  |  | NB-003 | Every reason-capture surface reads from this service; reasons are configurable per tenant | Not started
NB-012 | E02 Design System & UI Kit | Design System | Tokenise DESIGN.md into a theme package | All --nb-* colour, spacing, radius, elevation and motion tokens as a shared package. |  | All | Shared | Frontend | Must | MVP | 5 | 1 |  |  |  | Token package published; visual diff vs wireframe under 2px | Not started
NB-013 | E02 Design System & UI Kit | Design System | Core controls — button, input, select, segmented, chip | Per DESIGN.md 8.1-8.4 with every rest/hover/active/focus/disabled/loading state. |  | All | Shared | Frontend | Must | MVP | 8 | 2 |  |  | NB-012 | Storybook covers every state; a11y checks pass | Not started
NB-014 | E02 Design System & UI Kit | Design System | Containers — card, table, mobile list row, drawer, modal, bottom sheet | Per 8.5-8.13 including the sub-768px table-to-card replacement. |  | All | Shared | Frontend | Must | MVP | 8 | 2 |  |  | NB-012 | Responsive switch verified at 767/768px; focus trap correct | Not started
NB-015 | E02 Design System & UI Kit | Design System | Clinical state system — pill, badge, critical shape cue | Nine states, each hue + icon + text; critical adds a shape cue and a 3px left bar. |  | All | Shared | Frontend | Must | MVP | 5 | 3 |  |  | NB-012 | Colour-blind simulation review passed; no hue-only state anywhere | Not started
NB-016 | E02 Design System & UI Kit | Design System | Icon sprite & illustration tier | Single monoline family at stroke 1.75; 3D illustration set reserved for empty and success states only. |  | All | Shared | Frontend | Must | MVP | 3 | 2 |  |  | NB-012 | Sprite built from the wireframe symbols; lint blocks a second UI icon family | Not started
NB-017 | E02 Design System & UI Kit | Design System | App shell — sidebar, sectioned nav, rail, top bar, bottom nav | 248px sidebar / 72px collapsed / 88px rail / 64px bottom nav, with section grouping for the platform console. | SSA-02 | All | Shared | Frontend | Must | MVP | 8 | 3 |  |  | NB-014, NB-013 | Shell renders at all four breakpoints; nav sections group correctly | Not started
NB-018 | E02 Design System & UI Kit | Design System | Messaging component set | Message bubble, template card with variable-only editing, interactive reply set, conversation row, delivery-state chip, session-window indicator (8.16-8.21). | RCP-11,CMP-07 | All | Shared | Frontend | Must | MVP | 8 | 6 |  |  | NB-013, NB-014 | Template card makes fixed text physically uneditable; session indicator gates the composer | Not started
NB-019 | E02 Design System & UI Kit | Design System | Command palette (Cmd/Ctrl-K) | Grouped, role-scoped results. Platform console searches clinics, tickets, invoices and provisioning jobs. |  | All | Shared | Frontend | Should | MVP | 5 | 8 |  |  | NB-017 | Only permitted entities appear for the signed-in role | Not started
NB-020 | E02 Design System & UI Kit | Design System | Loading, empty, error, offline & permission state patterns | Skeleton shimmer, 140px illustration empties, inline errors, sync banner, absent-not-disabled permission handling. | NFR-12 | All | Shared | Frontend | Must | MVP | 5 | 4 |  |  | NB-014 | Every list screen implements all states; no disabled element carries a permission reason | Not started
NB-021 | E02 Design System & UI Kit | Design System | Light theme build | DESIGN.md 1.7 mapping. Blocked on stakeholder approval — still marked NEEDS APPROVAL in the source. |  | All | Shared | Frontend | Could | Phase 2 | 5 | 19 |  |  | NB-012 | Light theme passes AA on all tokens; per-user toggle persists | Not started
NB-022 | E03 Chart & Data-Visualisation System | Charts | Chart colour foundation & series palette | Eight categorical series in the OKLCH 0.49-0.53 band, sequential and diverging ramps, neutral diverging midpoint. Reserved state colours never appear as a series. | GP-03,PED-03 | All | Shared | Frontend | Must | MVP | 8 | 5 |  |  | NB-012 | All eight series at 3:1 on surface-1; automated check rejects any state colour used as series identity | Not started
NB-023 | E03 Chart & Data-Visualisation System | Charts | All-pairs gate & series-count guard | Only slots 1-3 clear the all-pairs gate; slots 4 and 6 must never share an all-pairs chart. Past three series, fold to Other or facet. | GP-03 | All | Shared | Frontend | Must | MVP | 5 | 5 |  |  | NB-022 | Component refuses a fourth series in scatter/bubble/small-multiple mode and folds to Other | Not started
NB-024 | E03 Chart & Data-Visualisation System | Charts | Column, bar, line & area primitives | Inline SVG only, no charting library, no canvas. 24px max thickness, 2px surface gap, 2px line, markers with surface ring. | NFR-02 | All | Shared | Frontend | Must | MVP | 8 | 6 |  |  | NB-022 | No third-party chart library in the bundle; renders under budget on a mid-range Android | Not started
NB-025 | E03 Chart & Data-Visualisation System | Charts | Stat tile, meter & sparkline | Auto-compacted values (1,284 / 12.9K / Rs 4.2L), signed delta coloured by direction and whether up is good. | OWN-01 | Owner | Shared | Frontend | Must | MVP | 5 | 6 |  |  | NB-022 | Compaction correct for INR lakh and SAR conventions in all three languages | Not started
NB-026 | E03 Chart & Data-Visualisation System | Charts | Legend, direct labels, tooltip & crosshair | Reuses the 8.9 tooltip surface. Labels never wear the series colour; a label that will not fit moves or drops to the tooltip, never clips. |  | All | Shared | Frontend | Must | MVP | 5 | 7 |  |  | NB-024 | No clipped label at any breakpoint; single-series charts render no legend | Not started
NB-027 | E03 Chart & Data-Visualisation System | Charts | Mandatory table view & export path for every chart | Every chart ships a table view — the sub-3:1 relief channel, the screen-reader equivalent and the export path. | SYS-23 | All | Shared | Frontend | Must | MVP | 5 | 7 |  |  | NB-024 | No chart ships without a table view; screen reader reads the table, not the SVG | Not started
NB-028 | E03 Chart & Data-Visualisation System | Charts | Ten chart states | Empty with reason, single data point, insufficient data, loading, offline/stale, partial data (gaps stay gaps), unit-ambiguous, threshold band, permission-restricted, subscription-unavailable. | PED-03,GP-03 | All | Shared | Frontend | Must | MVP | 8 | 8 |  |  | NB-024, NB-020 | All ten states demonstrated; a one-point trend degrades to a stat tile rather than erroring | Not started
NB-029 | E03 Chart & Data-Visualisation System | Charts | Chart RTL & aggregation rules | Time axes never mirror; category axes and legends do. Charts past ~200 marks aggregate before rendering and say so. | NFR-02 | All | Shared | Frontend | Must | MVP | 5 | 9 |  |  | NB-024, NB-031 | Arabic time-axis chart verified unmirrored; 500-mark dataset aggregates with a visible notice | Not started
NB-030 | E04 Localisation, RTL & i18n | i18n | i18n framework & string extraction pipeline | EN / AR / HI bundles plus the patient-side language set (Hinglish, Tamil, Malayalam, Kannada, Bengali). No hardcoded strings. | PAT-15 | All | Shared | Frontend | Must | MVP | 8 | 3 |  |  | NB-017 | Lint fails on literal UI strings; pseudo-locale build available | Not started
NB-031 | E04 Localisation, RTL & i18n | i18n | RTL layout engine — logical properties only | No left/right in shipped CSS. Nav, drawer, table order, chevrons and selected bar all mirror. |  | All | Shared | Frontend | Must | MVP | 8 | 4 |  |  | NB-030, NB-017 | Stylelint blocks physical properties; RTL screenshot suite passes | Not started
NB-032 | E04 Localisation, RTL & i18n | i18n | RTL non-mirroring exception list including anatomy | Clock glyphs, media, pulse mark, all time axes, phone numbers, Latin IDs, illustrations — and anatomy: the dental arch and dermatology body map keep fixed LTR order with both ends labelled. | DENT-01,DERM-04 | All | Shared | Frontend | Must | MVP | 5 | 5 |  |  | NB-031 | Dental arch and body map verified unmirrored in Arabic with explicit end labels | Not started
NB-033 | E04 Localisation, RTL & i18n | i18n | Arabic & Devanagari typography | IBM Plex Sans Arabic pairing, line-height +0.1em, letter-spacing forced to zero. |  | All | Shared | Frontend | Must | MVP | 3 | 4 |  |  | NB-030 | Arabic renders untracked; no clipped descenders | Not started
NB-034 | E04 Localisation, RTL & i18n | i18n | Hijri + Gregorian dual calendar | KSA tenants show Hijri primary with Gregorian secondary on one line; India Gregorian only. |  | Reception,Doctor,Owner | Shared | Frontend | Must | MVP | 5 | 5 |  |  | NB-030 | Date component unit-tested across both regions and month boundaries | Not started
NB-035 | E04 Localisation, RTL & i18n | i18n | Number, currency & numeral configuration | Western digits by default for clinical and financial values; INR en-IN grouping vs SAR trailing symbol. Arabic-Indic tenant-configurable. |  | Reception,Owner | Shared | Frontend | Must | MVP | 3 | 5 |  |  | NB-030 | Currency formatting matches the wireframe for both regions | Not started
NB-036 | E04 Localisation, RTL & i18n | i18n | Ramadan & prayer-time schedule mode | Prayer breaks and Ramadan hours change slot generation for KSA tenants. | SYS-04,CAD-05 | Reception,Doctor | Clinic | Fullstack | Must | MVP | 5 | 8 |  |  | NB-090 | Prayer blocks appear as non-bookable; Ramadan toggle shifts the whole day template | Not started
NB-037 | E04 Localisation, RTL & i18n | i18n | String-expansion resilience pass | ~30% expansion in Hindi and Arabic; every label container wraps, none truncate below two lines. |  | All | Shared | Frontend | Should | MVP | 3 | 7 |  |  | NB-030 | Pseudo-locale run shows zero truncation defects | Not started
NB-038 | E04 Localisation, RTL & i18n | i18n | Clinical & regulatory terminology review | Native clinician review of Arabic and Hindi clinical strings. Mistranslation here is a patient-safety risk. |  | Doctor,Nurse | Shared | QA | Must | MVP | 5 | 16 |  |  | NB-030, NB-103 | Sign-off from a licensed reviewer per language | Not started
NB-039 | E04 Localisation, RTL & i18n | i18n | Voice-note handling on the patient channel | Patients send voice notes; the clinic receives them transcribed or playable without leaving the inbox. | PAT-15 | Patient,Reception | Patient | Fullstack | Should | Phase 2 | 8 | 17 |  |  | NB-197, NB-030 | Voice note playable in the shared inbox; transcription failure degrades gracefully to audio | Not started
NB-040 | E05 Identity, Auth & Session | Auth | Staff authentication — WhatsApp OTP, short PIN, authenticator app | The three supported methods. NFR-06 explicitly rules out SSO and hardware security keys — do not build them. | NFR-06,SYS-01 | All | Shared | Security | Must | MVP | 8 | 2 |  |  | NB-001, NB-003 | All three methods work; no SSO or WebAuthn code path exists; OWASP ASVS L2 auth controls verified | Done
NB-041 | E05 Identity, Auth & Session | Auth | Dual-channel staff identity — verified email + mobile | Mobile receives the WhatsApp OTP, email receives the activation link. Both are required before any patient data is reachable. | CAD-12 | All | Shared | Security | Must | MVP | 5 | 3 |  |  | NB-040 | Access to patient data is impossible until both channels are verified | Done
NB-042 | E05 Identity, Auth & Session | Auth | Authenticator-app MFA enforcement | Mandatory for Owner, Platform operators and anyone holding refund or discount rights. | NFR-06 | Owner,Platform | Shared | Security | Must | MVP | 5 | 4 |  |  | NB-040 | MFA enforced by policy; recovery codes single-use | Done
NB-043 | E05 Identity, Auth & Session | Auth | Session management & device trust | Short-lived access token, rotating refresh, per-device session list, remote revoke. |  | All | Shared | Security | Must | MVP | 5 | 3 |  |  | NB-040 | Revoked session denied within 60s; refresh-token reuse detected | Done
NB-044 | E05 Identity, Auth & Session | Auth | Idle timeout & clinical screen lock | Shared clinic workstations auto-lock with fast re-auth and no loss of draft clinical notes. |  | Reception,Nurse,Doctor | Clinic | Frontend | Must | MVP | 3 | 6 |  |  | NB-043 | Draft consultation notes survive lock and unlock | Done
NB-045 | E05 Identity, Auth & Session | Auth | Staff invite, onboarding & first sign-in | Matches the Invited / Pending first sign-in state in the Staff wireframe. | CAD-12 | Owner | Clinic | Fullstack | Must | MVP | 5 | 7 |  |  | NB-041, NB-049 | Invite expires in 72h, single use, audited | Done
NB-046 | E05 Identity, Auth & Session | Auth | Password/PIN reset & account recovery | Rate-limited, token-based, no user enumeration. |  | All | Shared | Security | Must | MVP | 3 | 5 |  |  | NB-040 | Timing and copy identical for known and unknown accounts | Done
NB-047 | E05 Identity, Auth & Session | Auth | Staff suspension & immediate session termination | A suspended staff member loses access on every device at once. |  | Owner | Clinic | Backend | Must | MVP | 3 | 7 |  |  | NB-043, NB-045 | Suspension kills live sessions within 30s and writes an audit event | Done
NB-048 | E05 Identity, Auth & Session | Auth | Break-glass emergency access | Time-boxed elevated access with mandatory reason and loud audit alerting. | SYS-13 | Doctor,Owner | Clinic | Security | Should | Phase 2 | 5 | 15 |  |  | NB-049, NB-238 | Break-glass expires automatically; owner notified in real time | Done
NB-049 | E06 RBAC & Permissions | RBAC | Clinic role & permission model (10 modules x 7 actions) | Patients, Queue, Clinical, Billing, Packages, Pharmacy, Reports, Staff & Access, Setup, Compliance across Owner / Doctor / Reception / Nurse / Custom. |  | All | Clinic | Backend | Must | MVP | 8 | 4 |  |  | NB-003 | Matrix matches the wireframe PERMS fixture exactly; unit-tested per role | Done
NB-050 | E06 RBAC & Permissions | RBAC | Server-side policy enforcement point | Deny by default on every endpoint. No client-only gating anywhere. |  | All | Shared | Security | Must | MVP | 8 | 5 |  |  | NB-049, NB-040 | Automated test asserts 403 for every role/endpoint pair not granted | Done
NB-051 | E06 RBAC & Permissions | RBAC | Row-level scoping — own patients vs all clinic patients | Enforced in the query, not by post-filtering. |  | Doctor | Clinic | Backend | Must | MVP | 8 | 6 |  |  | NB-050 | Direct-ID access to another doctor's patient returns 404, not 403 | Done
NB-052 | E06 RBAC & Permissions | RBAC | Field-level restrictions | No financial fields, no refund, no discount, vitals-and-vaccines-only custom grants. |  | Reception,Nurse | Clinic | Backend | Must | MVP | 5 | 6 |  |  | NB-050 | Restricted fields are absent from the API response, not merely hidden | Done
NB-053 | E06 RBAC & Permissions | RBAC | Consent checked at query level | Consent state is evaluated in the data access path, not in the UI — a withdrawn consent removes the data from results. | NFR-08,CMP-02 | All | Shared | Backend | Must | MVP | 8 | 7 |  |  | NB-050, NB-003 | Query-level consent check demonstrated; bypassing the UI does not expose consent-gated data | Done
NB-054 | E06 RBAC & Permissions | RBAC | UI permission rendering contract | Permission-restricted elements are absent, never disabled or greyed. | SSA-02 | All | Shared | Frontend | Must | MVP | 5 | 6 |  |  | NB-050, NB-013 | Automated DOM assertion: no disabled element carries a permission reason; no create button exists for roles without create rights | Done
NB-055 | E06 RBAC & Permissions | RBAC | Custom role builder & permission matrix UI | Owner-facing 640px matrix modal for bespoke roles. |  | Owner | Clinic | Frontend | Should | MVP | 8 | 9 |  |  | NB-049 | Owner can reproduce the wireframe's Front Desk + Vitals role | Done
NB-056 | E06 RBAC & Permissions | RBAC | Approval workflows & maker-checker | Refunds, discounts above threshold, clinical amendments and platform discount approvals all need a second approver. | SYS-06 | Owner,Reception | Shared | Fullstack | Must | MVP | 8 | 10 |  |  | NB-050, NB-238 | Self-approval blocked; approval chain visible in the audit log | Done
NB-057 | E06 RBAC & Permissions | RBAC | Delegation & temporary access grants | Cover a doctor's leave without permanently widening rights; auto-expiring. |  | Owner | Clinic | Backend | Could | Phase 2 | 5 | 18 |  |  | NB-049 | Grant expires on schedule and the expiry is audited | Done
NB-058 | E06 RBAC & Permissions | RBAC | Subscription vs permission state separation | Subscription-unavailable modules appear only in Catalog/Plan/Setup with historical data still readable; permission-restricted ones vanish entirely. | DENT-06,DENT-07,DERM-04,DERM-07 | All | Shared | Frontend | Must | MVP | 5 | 9 |  |  | NB-008, NB-054 | Both states verified; ending a trial leaves historical data readable | Not started
NB-059 | E06 RBAC & Permissions | RBAC | Staff & Access screen | Staff list, status, scope summary, last-seen and role chips. |  | Owner | Clinic | Frontend | Must | MVP | 5 | 9 |  |  | NB-049, NB-045 | Screen matches the wireframe; every action permission-gated | Done
NB-060 | E07 Clinic Setup & Administration | Setup | Guided clinic setup wizard — skippable and resumable | Welcome, clinic profile, and the remaining steps. Every step can be skipped and resumed; fully self-serve with no support intervention. | CAD-01,SYS-21,NFR-18 | Owner | Clinic | Fullstack | Must | MVP | 13 | 7 |  |  | NB-261, NB-017 | A new clinic goes live unaided; closing the wizard mid-way and returning resumes at the same step | Done
NB-061 | E07 Clinic Setup & Administration | Setup | Charge head / price master management | Effective-dated service codes, categories, INR/SAR prices, GST/VAT rates, package eligibility and active flag. | CAD-04 | Owner | Clinic | Fullstack | Must | MVP | 8 | 8 |  |  | NB-010 | Reproduces the wireframe's 24 charge heads with effective-dated pricing | Done
NB-062 | E07 Clinic Setup & Administration | Setup | Simple policy settings | Clinic-level operational policies exposed as plain settings, not a rules engine. | CAD-06 | Owner | Clinic | Fullstack | Must | MVP | 5 | 10 |  |  | NB-060 | Policy changes take effect without a redeploy and are audited | Done
NB-063 | E07 Clinic Setup & Administration | Setup | Consent & privacy notice contact settings | Contact details only — the template library itself lives in Compliance & Audit. | CAD-08 | Owner | Clinic | Frontend | Must | MVP | 3 | 11 |  |  | NB-240 | Only contact fields are editable here; the library is reachable but not duplicated | Done
NB-064 | E07 Clinic Setup & Administration | Setup | Clinic schedule & calendar administration | Working hours, visit-type durations, holidays and clinic-wide calendar rules. | CAD-05 | Owner | Clinic | Fullstack | Must | MVP | 8 | 8 |  |  | NB-060 | Visit-type durations drive slot generation; holidays block booking | Done
NB-065 | E07 Clinic Setup & Administration | Setup | Shift timings & attendance | Staff shift patterns and attendance capture. | CAD-09 | Owner | Clinic | Fullstack | Could | Phase 2 | 8 | 19 |  |  | NB-092 | Shift roster drives the payroll export; attendance editable with audit | Done
NB-066 | E07 Clinic Setup & Administration | Setup | Simple payroll export | CSV of days, hours, salary and notes with optional PF/ESI columns. There is deliberately no payroll engine. | CAD-10 | Owner | Clinic | Fullstack | Should | MVP | 5 | 17 |  |  | NB-092 | CSV opens in Excel without cleanup; no calculation engine is built | Done
NB-067 | E07 Clinic Setup & Administration | Setup | Tenant subscription & plan self-service | Current plan, usage against limits, and upgrade or downgrade taking effect in under five minutes with no data loss. | CAD-13,SYS-20 | Owner | Clinic | Fullstack | Should | Phase 3 | 8 | 20 |  |  | NB-008, NB-269 | Plan change completes under 5 minutes; no data is lost in either direction | Done
NB-068 | E07 Clinic Setup & Administration | Setup | Self-serve data import & export | Import wizard and full export without support involvement. | SYS-23,NFR-18 | Owner | Clinic | Fullstack | Must | MVP | 8 | 15 |  |  | NB-003, NB-071 | Import dry-runs before writing; export completes unaided | Done
NB-069 | E07 Clinic Setup & Administration | Setup | Setup completeness checklist | The clinic sees what is still outstanding — price master, WhatsApp number, screen pairing — with a direct route to each. | CAD-01,RCP-14,CAD-07 | Owner | Clinic | Frontend | Should | MVP | 3 | 12 |  |  | NB-060 | Checklist state derives from real configuration, never a manual tick | Done
NB-070 | E07 Clinic Setup & Administration | Setup | Facility & licence registry | Clinic facility record, licence numbers and registration identifiers used on invoices and claim packs. | CMP-11,BIL-11 | Owner | Clinic | Backend | Must | MVP | 5 | 11 |  |  | NB-060 | Licence number is available to the claim pack and invoice generators | Done
NB-071 | E08 Patient Records & Registration | Patients | Patient registration & demographics | Multi-script names, phone, DOB, gender, guardian, address and national ID (Aadhaar / Iqama) handling. | PAT-01 | Reception | Clinic | Fullstack | Must | MVP | 8 | 6 |  |  | NB-003, NB-013 | Arabic and Devanagari names store, search and print correctly | Done
NB-072 | E08 Patient Records & Registration | Patients | Duplicate detection & supervised merge | Fuzzy match on registration; merge preserves every encounter and invoice and is reversible. |  | Reception,Owner | Clinic | Backend | Must | MVP | 8 | 11 |  |  | NB-071 | Merge is reversible for 30 days and fully audited | Done
NB-073 | E08 Patient Records & Registration | Patients | Patient search & directory | Fast search by phone, name, token or MRN across scripts, scoped by role. |  | Reception,Doctor,Nurse | Clinic | Fullstack | Must | MVP | 5 | 7 |  |  | NB-071 | p95 search under 300ms on 200k patients | Done
NB-074 | E08 Patient Records & Registration | Patients | Patient 360 context drawer | Identity, allergies, chronic conditions, active packages, outstanding balance, last visit. | GP-02 | Doctor,Nurse,Reception | Clinic | Frontend | Must | MVP | 8 | 9 |  |  | NB-071, NB-051 | Opens under 500ms; allergy banner always visible | Done
NB-075 | E08 Patient Records & Registration | Patients | Patient document & report attachments | Upload, virus scan, thumbnail and retention policy; feeds External Reports. | SYS-18 | Doctor,Nurse | Clinic | Fullstack | Must | MVP | 5 | 12 |  |  | NB-071, NB-292 | Malicious file rejected; files encrypted at rest with the tenant key | Not started
NB-076 | E08 Patient Records & Registration | Patients | Secure file delivery via expiring link | A file is never sent into an open chat. Delivery is always an expiring, access-logged link. | SYS-18,PAT-13 | Reception,Doctor,Patient | Shared | Backend | Must | MVP | 5 | 12 |  |  | NB-292 | No attachment is ever posted inline; link expires and every access is logged | Not started
NB-077 | E08 Patient Records & Registration | Patients | Chronic condition & problem list | Carried forward between encounters and driving chronic-review due lists. | GP-02 | Doctor | Clinic | Fullstack | Must | MVP | 5 | 12 |  |  | NB-071 | Chronic review due list is derived, not manually maintained | Done
NB-078 | E08 Patient Records & Registration | Patients | Patient data export & erasure execution | Subject-access export and erasure honouring clinical retention and legal hold. | CMP-03,PAT-14,NFR-07 | Owner | Shared | Backend | Must | MVP | 5 | 16 |  |  | NB-238, NB-071 | Export delivered within 72h as an expiring link; erasure respects statutory retention | Not started
NB-079 | E08 Patient Records & Registration | Patients | Source tagging & attribution capture | One source tag per visit, never a dual axis. Feeds the owner's where-patients-come-from view. | OWN-02,MKT-04 | Reception | Clinic | Backend | Should | MVP | 3 | 13 |  |  | NB-071 | Exactly one source tag per visit is enforced at write time | Done
NB-080 | E09 Caregiver, Family & Guardianship | Family | One WhatsApp number, whole family | A single member number shows no picker at all; multi-member numbers gain one. Booking stays within the six-tap budget. | CGV-01,PAT-03 | Patient | Patient | Fullstack | Must | MVP | 8 | 14 |  |  | NB-201, NB-071 | Single-member numbers never see a picker; booking completes in six taps or fewer | Not started
NB-081 | E09 Caregiver, Family & Guardianship | Family | Add family member with consent capture | Five-step in-chat flow ending in explicit consent for that member. | CGV-02 | Patient | Patient | Fullstack | Must | MVP | 8 | 14 |  |  | NB-080, NB-242 | Member cannot be added without recorded consent; each step is resumable | Done
NB-082 | E09 Caregiver, Family & Guardianship | Family | Minor & guardian handling with age-18 handover | Turning 18 automatically raises a guardian-access review task and moves consent to the patient. | CGV-03,PED-06,CMP-04 | Patient,Reception | Patient | Fullstack | Must | MVP | 8 | 15 |  |  | NB-081 | Age-18 transition fires automatically; consent stored separately per guardian | Done
NB-083 | E09 Caregiver, Family & Guardianship | Family | Proxy booking, check-in & queue updates | A caregiver books and checks in for another member; reminders always name the actual patient. | CGV-04 | Patient | Patient | Fullstack | Must | MVP | 5 | 15 |  |  | NB-080, NB-202 | Reminders name the patient, never the caregiver | Not started
NB-084 | E09 Caregiver, Family & Guardianship | Family | Dual delivery of visit instructions | Instructions reach both the patient and the nominated caregiver. | CGV-05 | Patient | Patient | Fullstack | Should | MVP | 5 | 16 |  |  | NB-083 | Both recipients receive the message; delivery state tracked per recipient | Not started
NB-085 | E09 Caregiver, Family & Guardianship | Family | Proxy revocation & scope change | A patient can revoke or narrow a caregiver's access at any time. | CGV-06 | Patient | Patient | Fullstack | Must | MVP | 5 | 16 |  |  | NB-081 | Revocation takes effect immediately across every surface and is audited | Done
NB-086 | E09 Caregiver, Family & Guardianship | Family | Family appointment batching | Booking several family members into adjacent slots, degrading honestly when only some are free. | CGV-07 | Patient,Reception | Patient | Fullstack | Should | Phase 2 | 8 | 18 |  |  | NB-083 | Partial availability is stated explicitly rather than silently dropping a member | Not started
NB-087 | E09 Caregiver, Family & Guardianship | Family | Elderly-parent care alerts | Adult children receive care alerts for an elderly parent within the consented scope. | CGV-09 | Patient | Patient | Fullstack | Could | Phase 2 | 5 | 19 |  |  | NB-085 | Alerts respect the consent scope and stop on revocation | Not started
NB-088 | E09 Caregiver, Family & Guardianship | Family | Family plan / package sharing | Sharing package sessions across family members. | CGV-10,PAT-24,CEO-15 | Patient,Reception | Patient | Fullstack | Could | Phase 3 | 8 | 21 |  |  | NB-153, NB-080 | Positioned as a booking and check-in convenience plan, never a clinical care contract | Not started
NB-089 | E09 Caregiver, Family & Guardianship | Family | Child marketing block across every module | Child profiles never receive marketing, enforced pre-emptively at campaign check. | DPO-09,CMP-04 | All | Shared | Backend | Must | MVP | 5 | 15 |  |  | NB-053, NB-082 | Campaign send to a child profile is impossible; the block is enforced server-side | Not started
NB-090 | E10 Queue, Scheduling & Availability | Scheduling | Appointment scheduling engine | Slot generation, doctor calendars, breaks, prayer time, leave and blocked slots. | CAD-05,SYS-04 | Reception | Clinic | Backend | Must | MVP | 13 | 7 |  |  | NB-003, NB-071 | No double-booking under concurrent booking load | Done
NB-091 | E10 Queue, Scheduling & Availability | Scheduling | Doctor availability, leave & block management | Doctor-side supply management that supplements rather than replaces the appointment book. | DOC-03,CAD-05 | Doctor,Owner | Clinic | Fullstack | Must | MVP | 8 | 9 |  |  | NB-090 | Blocking a doctor warns about affected package sessions restricted to that doctor | Done
NB-092 | E10 Queue, Scheduling & Availability | Scheduling | Roster, shifts, exceptions & holidays | Weekly roster with per-day exceptions and clinic holidays. | CAD-05,CAD-09 | Owner | Clinic | Fullstack | Must | MVP | 8 | 10 |  |  | NB-064 | Exception overrides the roster for that date only | Done
NB-093 | E10 Queue, Scheduling & Availability | Queue | Token & walk-in queue management | Token issue, priority, reorder with mandatory reason and estimated wait. |  | Reception | Clinic | Fullstack | Must | MVP | 8 | 8 |  |  | NB-090 | Token numbers unique per day per doctor; reorder audited | Done
NB-094 | E10 Queue, Scheduling & Availability | Queue | Queue state machine | Not arrived, checked in, waiting, vitals pending/done, in consultation, checkout pending, completed, no-show. |  | Reception,Nurse,Doctor | Clinic | Backend | Must | MVP | 5 | 8 |  |  | NB-093 | Illegal transitions rejected; every transition audited | Done
NB-095 | E10 Queue, Scheduling & Availability | Queue | Today / Arrivals screen | Reception landing with arrivals, badges and quick check-in. |  | Reception | Clinic | Frontend | Must | MVP | 5 | 9 |  |  | NB-094, NB-017 | Matches the wireframe; live-updates without refresh | Done
NB-096 | E10 Queue, Scheduling & Availability | Queue | Real-time queue sync | All roles see the same queue state within two seconds, degrading to polling. | NFR-12 | All | Clinic | Backend | Must | MVP | 5 | 9 |  |  | NB-094 | 2s propagation at 100 concurrent clients; fallback verified | Not started
NB-097 | E10 Queue, Scheduling & Availability | Queue | Cancellation, reschedule & no-show handling | Reason codes drawn from the shared reason list. | SYS-07 | Reception | Clinic | Fullstack | Must | MVP | 5 | 10 |  |  | NB-090, NB-011 | Reason mandatory; slot released immediately | Done
NB-098 | E10 Queue, Scheduling & Availability | Queue | Smart overbooking protection | Session caps count walk-ins and booked patients together; a full session is refused rather than silently overbooked. | PAT-19 | Reception,Patient | Clinic | Backend | Must | MVP | 5 | 11 |  |  | NB-090, NB-094 | Cap counts both intake paths; overbooking attempt is refused with a clear reason | Done
NB-099 | E10 Queue, Scheduling & Availability | Queue | Waitlist & auto-fill offers | A freed slot is offered to the waitlist with a 15-minute expiry. | PAT-07,SYS-06 | Reception,Patient | Clinic | Fullstack | Should | MVP | 8 | 12 |  |  | NB-090, NB-097 | Offer expires in 15 minutes and is re-offered in order; no double allocation | Done
NB-100 | E10 Queue, Scheduling & Availability | Queue | Doctor delay broadcast ladder & clear-delay | Two-step confirm writing the delay then closing and appending to history, with a Clear delay action. Treated as operationally urgent — not held for a prayer window. | RCP-04,SYS-03 | Reception | Clinic | Fullstack | Must | MVP | 8 | 13 |  |  | NB-094, NB-195 | Clear delay stops the announcement; delay broadcast bypasses the prayer-window hold | Done
NB-101 | E10 Queue, Scheduling & Availability | Queue | Wait-time estimation | Estimated wait derived from historical consultation durations per doctor. | PAT-05 | Reception,Patient | Clinic | Backend | Could | Phase 2 | 5 | 19 |  |  | NB-094 | Estimate within +/-25% on retrospective data | Done
NB-102 | E11 Clinical Workspace | Clinical | Consultation workspace shell & session strip | The doctor's primary screen. The session strip shows status before any detail. | DOC-01 | Doctor | Clinic | Frontend | Must | MVP | 8 | 11 |  |  | NB-094, NB-074 | A full consultation completes without leaving the screen | Done
NB-103 | E11 Clinical Workspace | Clinical | Clinical note capture & templates | Structured plus free-text notes, per-specialty templates, autosave. | DOC-05 | Doctor | Clinic | Fullstack | Must | MVP | 8 | 11 |  |  | NB-102 | No note loss on crash or lock; autosave every 10s | Done
NB-104 | E11 Clinical Workspace | Clinical | Clinical note amendment & versioning | Signed notes are immutable; amendments append with reason and author. | SYS-13 | Doctor | Clinic | Backend | Must | MVP | 5 | 12 |  |  | NB-103, NB-238 | Original text always retrievable; amendment reason mandatory | Done
NB-105 | E11 Clinical Workspace | Clinical | Previous medicines & treatment view | Read before prescribing — prior therapy surfaced in the prescribing path. | DOC-02,GP-06 | Doctor | Clinic | Frontend | Must | MVP | 5 | 12 |  |  | NB-102, NB-109 | Prior medication is visible without leaving the prescription pad | Done
NB-106 | E11 Clinical Workspace | Clinical | Vitals capture & charting | Age-appropriate ranges with out-of-range flagging; latest weight feeds paediatric dosing. | PED-05 | Nurse,Doctor | Clinic | Fullstack | Must | MVP | 5 | 10 |  |  | NB-074, NB-094 | Abnormal values carry the critical clinical state; latest weight is exposed to the dose calculator | Done
NB-107 | E11 Clinical Workspace | Clinical | Allergy register with graded severity | Allergy registry with severity grading and a persistent banner. | DERM-05 | Doctor,Nurse | Clinic | Fullstack | Must | MVP | 8 | 12 |  |  | NB-074 | Allergy banner always visible; severity grade drives warning strength | Done
NB-108 | E11 Clinical Workspace | Clinical | Allergy hard-warning with mandatory override reason | A conflicting prescription cannot be issued without a documented override reason. | DERM-05 | Doctor | Clinic | Fullstack | Must | MVP | 5 | 13 |  |  | NB-107, NB-109 | Override is impossible without a reason; every override is audited | Done
NB-109 | E11 Clinical Workspace | Clinical | Fast e-prescription pad | The prescribing surface itself, built for speed. | DOC-06,GP-06 | Doctor | Clinic | Fullstack | Must | MVP | 8 | 12 |  |  | NB-102, NB-010 | A routine prescription completes within the target keystroke budget | Done
NB-110 | E11 Clinical Workspace | Clinical | Generic-name prescribing preference — India | Generic name printed first per the India NMC norm, brand permitted in brackets, search matches both. | GP-05 | Doctor | Clinic | Fullstack | Must | MVP | 5 | 13 |  |  | NB-109 | Generic-first print verified; search matches brand and generic | Not started
NB-111 | E11 Clinical Workspace | Clinical | Schedule H/H1 and SFDA controlled-substance rules | India Schedule H/H1 caution applied automatically; KSA uses SFDA identifiers and controlled rules. | GP-05,DOC-06 | Doctor | Clinic | Backend | Must | MVP | 5 | 13 |  |  | NB-109, NB-010 | Correct rule set applies automatically by tenant region | Done
NB-112 | E11 Clinical Workspace | Clinical | Weight-based paediatric dosing | Dose calculated from the latest recorded weight, sourced from a validated rule set rather than ad-hoc UI arithmetic. | PED-05 | Doctor | Clinic | Fullstack | Must | MVP | 8 | 14 |  |  | NB-109, NB-106 | Dose derives from the latest recorded weight; the rule source is named and versioned | Done
NB-113 | E11 Clinical Workspace | Clinical | Pregnancy & lactation warnings | Fires without requiring the Gynaecology profile to be enabled. | GYN-03 | Doctor | Clinic | Fullstack | Must | MVP | 5 | 14 |  |  | NB-109 | Warning fires for any patient of childbearing potential regardless of specialty profile | Done
NB-114 | E11 Clinical Workspace | Clinical | Favourite Rx sets | Saved prescription sets per doctor. | GP-06 | Doctor | Clinic | Fullstack | Should | MVP | 5 | 14 |  |  | NB-109 | Sets are per doctor with clinic defaults; applying a set still runs every safety check | Done
NB-115 | E11 Clinical Workspace | Clinical | Diagnosis coding & encounter timeline | ICD-10 search and a chronological encounter history respecting row-level scope. |  | Doctor,Nurse | Clinic | Fullstack | Must | MVP | 5 | 13 |  |  | NB-103, NB-010 | Coded diagnosis flows to reports; timeline paginates to five years | Done
NB-116 | E11 Clinical Workspace | Clinical | Follow-up scheduling & treatment-linked recall engine | Recall driven by the treatment performed, feeding reminders and the front-desk callback list on a miss. | PAT-20,DENT-06 | Doctor,Reception | Clinic | Fullstack | Must | MVP | 8 | 14 |  |  | NB-090, NB-102, NB-308 | Recall is derived from the procedure; a 15-day miss routes to the callback list | In progress
NB-117 | E11 Clinical Workspace | Clinical | Print & share visit outputs | Prescription, summary and instructions printed or shared, always via the secure link path. | DOC-11,SYS-18 | Doctor | Clinic | Fullstack | Must | MVP | 5 | 15 |  |  | NB-103, NB-076 | Output carries clinic letterhead and doctor registration number | Not started
NB-118 | E11 Clinical Workspace | Clinical | Referral letters & medical certificates | Referral letter generation and medical / sick-leave certificates. | GP-04,GP-07 | Doctor | Clinic | Fullstack | Should | MVP | 5 | 15 |  |  | NB-117 | Generated PDF is valid in both regions and in all three languages | Not started
NB-119 | E11 Clinical Workspace | Clinical | Procedure consent capture & signature | Signed consent gates the procedure — it cannot proceed unsigned. | DOC-09 | Doctor,Nurse | Clinic | Fullstack | Must | MVP | 5 | 15 |  |  | NB-102, NB-242 | Procedure cannot be started without a recorded signature | Done
NB-120 | E11 Clinical Workspace | Clinical | Clinical settings per doctor and clinic | Note defaults, favourite drugs, template management, consultation duration, dental numbering system. | DENT-01 | Doctor,Owner | Clinic | Frontend | Should | MVP | 3 | 15 |  |  | NB-103 | Dental numbering is chosen once clinic-wide; storage stays FDI-keyed and switching loses no data | Not started
NB-121 | E12 Specialty Workspaces | Specialty | Specialty profile framework & entitlement gating | Per-specialty workspaces switched on by profile and subscription; historical data stays readable when a trial ends. | DENT-06,DENT-07,DERM-04,DERM-07 | Doctor | Clinic | Fullstack | Must | MVP | 8 | 14 |  |  | NB-103, NB-008 | Ending a trial locks new entry but leaves historical data readable | In progress
NB-122 | E12 Specialty Workspaces | Specialty | Dental chart — FDI storage with selectable display numbering | Numbering chosen once clinic-wide; storage always keyed by FDI so switching loses no data. Includes supernumerary teeth. | DENT-01 | Doctor | Clinic | Fullstack | Must | MVP | 13 | 15 |  |  | NB-121, NB-032 | Switching numbering system loses no data; supernumerary teeth are representable | Done
NB-123 | E12 Specialty Workspaces | Specialty | Tooth-linked radiograph library | Radiographs linked to a tooth and reachable directly from the chart. | DENT-02 | Doctor | Clinic | Fullstack | Must | MVP | 8 | 16 |  |  | NB-122, NB-075 | A radiograph opens from the tooth it belongs to in one tap | Not started
NB-124 | E12 Specialty Workspaces | Specialty | Implant & crown staging with lab work | Stage order shown as dashed outline plus superscript — form, not a new colour. | DENT-05 | Doctor | Clinic | Fullstack | Should | MVP | 8 | 16 |  |  | NB-122 | Stage order is conveyed without introducing a colour outside the palette | Not started
NB-125 | E12 Specialty Workspaces | Specialty | Orthodontic plans with auto-scheduled adjustments | Monthly adjustments scheduled through the recall engine; a 15-day miss routes to the front-desk callback list. | DENT-06,PAT-20 | Doctor | Clinic | Fullstack | Should | Phase 2 | 8 | 17 |  |  | NB-122, NB-116 | Adjustments auto-schedule; missed adjustment appears on the callback list | Not started
NB-126 | E12 Specialty Workspaces | Specialty | Dental treatment plan, estimate, approval & booking | Extends the price-transparency estimate flow into a staged dental plan. | DENT-07,BIL-07 | Doctor,Reception | Clinic | Fullstack | Should | Phase 2 | 8 | 17 |  |  | NB-122, NB-170 | Estimate converts to an approved plan and then to bookings without re-entry | Not started
NB-127 | E12 Specialty Workspaces | Specialty | Per-tooth timeline | Everything ever done to a tooth — procedures, radiographs, medicines, materials — one tap from the chart. Roadmap state, not a purchasable upsell. | DENT-08 | Doctor | Clinic | Fullstack | Could | Phase 3 | 8 | 22 |  |  | NB-122 | Presented as a roadmap state and not offered for purchase | Done
NB-128 | E12 Specialty Workspaces | Specialty | Dermatology body map & photo capture | Fixed left-to-right anatomy with both ends labelled; photo series attached to a mapped site. | DERM-04 | Doctor | Clinic | Fullstack | Must | MVP | 8 | 16 |  |  | NB-121, NB-032 | Body map does not mirror in Arabic and carries explicit end labels | Not started
NB-129 | E12 Specialty Workspaces | Specialty | Dermatology reading appointment auto-creation | The reading appointment is created with the order — never a second manual step. | DERM-04 | Doctor,Reception | Clinic | Backend | Must | MVP | 5 | 16 |  |  | NB-128, NB-090 | Ordering creates the reading appointment atomically | Not started
NB-130 | E12 Specialty Workspaces | Specialty | Photo follow-up reminders | Timed photo requests back to the patient on the messaging channel. | DERM-06,SYS-11 | Doctor,Patient | Patient | Fullstack | Should | Phase 2 | 5 | 18 |  |  | NB-128, NB-197 | Reminder fires on schedule and the returned photo attaches to the correct site | Not started
NB-131 | E12 Specialty Workspaces | Specialty | Paediatric vaccination register & due lists | Vaccines due, given, overdue and catch-up, from a versioned clinical source. | PED-01,PED-08 | Nurse,Doctor | Clinic | Fullstack | Must | MVP | 8 | 15 |  |  | NB-121, NB-010 | Due and overdue derive from DOB and the regional schedule; content source is versioned | Not started
NB-132 | E12 Specialty Workspaces | Specialty | Paediatric growth tracking & faltering alerts | Growth charts plotted; faltering alerts triggered by a validated growth service, never calculated in the UI. | PED-03,PED-04 | Doctor | Clinic | Fullstack | Should | Phase 2 | 8 | 18 |  |  | NB-121, NB-024 | No growth percentile is computed client-side; the validated service is the only source | Not started
NB-133 | E12 Specialty Workspaces | Specialty | Paediatric parent reminders reconciled to one message | Vaccine and appointment reminders reconcile into a single parent message, never two. | PED-02 | Patient | Patient | Backend | Must | MVP | 5 | 16 |  |  | NB-131, NB-203 | Two due items on the same day produce exactly one message | Not started
NB-134 | E12 Specialty Workspaces | Specialty | Paediatric child-friendly profile view | Friendly avatar only, carrying no clinical data. | PED-07 | Patient | Patient | Frontend | Could | Phase 2 | 3 | 19 |  |  | NB-121 | No clinical value is rendered in the child-facing view | Not started
NB-135 | E12 Specialty Workspaces | Specialty | Orthopaedics — X-ray attach, review flag & fracture templates | Imaging attached with a review flag plus fracture and injury note templates. | ORTH-01,ORTH-02 | Doctor | Clinic | Fullstack | Should | MVP | 8 | 17 |  |  | NB-121, NB-075 | Unreviewed imaging stays flagged until a clinician clears it | Not started
NB-136 | E12 Specialty Workspaces | Specialty | Orthopaedics — physio session packages | Physio delivered as tracked package sessions with automatic pre-session reminders. | ORTH-03,PKG-12 | Doctor,Nurse | Clinic | Fullstack | Should | Phase 2 | 5 | 18 |  |  | NB-153 | Each session auto-reminds the patient beforehand | Not started
NB-137 | E12 Specialty Workspaces | Specialty | Gynaecology — pregnancy tracker | LMP to EDD timeline with visit scheduling along it. | GYN-01 | Doctor | Clinic | Fullstack | Should | Phase 2 | 8 | 18 |  |  | NB-121 | Timeline recalculates correctly when LMP is corrected | Not started
NB-138 | E12 Specialty Workspaces | Specialty | Gynaecology — ultrasound report attach & review | Report attachment with a review state. | GYN-02 | Doctor | Clinic | Fullstack | Should | Phase 2 | 5 | 18 |  |  | NB-121, NB-075 | Report attaches to the correct encounter with a review flag | Not started
NB-139 | E12 Specialty Workspaces | Specialty | ENT — endoscopy media, audiogram & minor-procedure notes | Endoscopy image/video attachment, audiogram entry and minor-procedure notes with consent. | ENT-01,ENT-02,ENT-03 | Doctor | Clinic | Fullstack | Could | Phase 2 | 8 | 19 |  |  | NB-121, NB-075 | Video attaches within the size policy; audiogram renders as a chart with a table view | Not started
NB-140 | E12 Specialty Workspaces | Specialty | Ayurveda — Panchakarma day strip & herbal formulations | Day-strip therapy plan (time axis, never mirrored) and herbal formulation prescribing. | AYU-02,AYU-03 | Doctor | Clinic | Fullstack | Could | Phase 2 | 8 | 20 |  |  | NB-121, NB-109 | Day strip does not mirror in Arabic; herbal formulations print correctly | Not started
NB-141 | E12 Specialty Workspaces | Specialty | Homeopathy — remedy & potency prescribing | Remedy with potency selection in the prescription pad. | HOM-02 | Doctor | Clinic | Fullstack | Could | Phase 2 | 5 | 20 |  |  | NB-121, NB-109 | Potency notation prints correctly and is searchable | Not started
NB-142 | E13 Nursing, Orders & Triage | Nursing | Arrivals & vitals worklist | Nurse landing screen with the pending-vitals queue. |  | Nurse | Clinic | Frontend | Must | MVP | 5 | 10 |  |  | NB-094, NB-106 | Matches the wireframe and updates live with queue state | Done
NB-143 | E13 Nursing, Orders & Triage | Nursing | Priority patients & urgent triage | Priority flagging with mandatory reason and critical-state styling. |  | Nurse | Clinic | Fullstack | Must | MVP | 5 | 11 |  |  | NB-094, NB-011 | Urgent flag reorders the queue and alerts the doctor | Done
NB-144 | E13 Nursing, Orders & Triage | Nursing | Clinical triage inbox | Nurse-facing triage of inbound patient messages, separate from the reception inbox. | NUR-05,RCP-11 | Nurse | Clinic | Fullstack | Must | MVP | 8 | 14 |  |  | NB-197 | Clinical questions route to the nurse, not reception; escalation path is explicit | Not started
NB-145 | E13 Nursing, Orders & Triage | Nursing | Administration orders & medication administration record | Injection and infusion orders with administer, witness and refuse-with-reason. |  | Nurse,Doctor | Clinic | Fullstack | Must | MVP | 8 | 13 |  |  | NB-102, NB-109 | Administration record immutable; five-rights checks enforced | Done
NB-146 | E13 Nursing, Orders & Triage | Nursing | Today's procedures worklist | Scheduled procedures, prep checklists and completion capture. |  | Nurse | Clinic | Fullstack | Should | MVP | 5 | 14 |  |  | NB-094 | Completion posts a billable event | Done
NB-147 | E13 Nursing, Orders & Triage | Nursing | Package session administration by nurse | The nurse marks a session delivered, decrementing sessions owed atomically. | PKG-10 | Nurse | Clinic | Fullstack | Must | MVP | 5 | 14 |  |  | NB-153 | Decrement is atomic, auditable and cannot over-consume under concurrency | Done
NB-148 | E13 Nursing, Orders & Triage | Nursing | Completed activity log | The nurse's own read-only record of the day's completed work. |  | Nurse | Clinic | Frontend | Should | MVP | 3 | 15 |  |  | NB-145 | Read-only and exportable for shift handover | Done
NB-149 | E13 Nursing, Orders & Triage | Nursing | Task handoff & escalation SLA | Doctor-to-nurse tasks with acknowledgement and escalation when overdue. |  | Nurse,Doctor | Clinic | Fullstack | Should | MVP | 5 | 15 |  |  | NB-144 | Unacknowledged critical task escalates within a configurable SLA | Not started
NB-150 | E14 Treatment Packages | Packages | Package definition builder (6-step) | Basic information, included items, pricing and savings, validity and eligibility, payment and refunds, preview and activate. |  | Owner | Clinic | Fullstack | Must | MVP | 13 | 12 |  |  | NB-061 | Reproduces the wireframe package definitions end to end | Done
NB-151 | E14 Treatment Packages | Packages | Package catalogue & lifecycle states | Draft, on sale, paused, retired, with version history for already-sold packages. |  | Owner | Clinic | Backend | Must | MVP | 5 | 12 |  |  | NB-150 | Retiring a package does not affect sold instances | Done
NB-152 | E14 Treatment Packages | Packages | Package sale flow (6-step) | Patient, package, eligibility, review, payment, invoice and card. |  | Reception | Clinic | Fullstack | Must | MVP | 8 | 13 |  |  | NB-150, NB-162 | Sale creates instance, invoice and correct tax lines for both regions | Done
NB-153 | E14 Treatment Packages | Packages | Package instance & session ledger | Sessions owed, consumed and expired, with validity window and grace period. | PKG-12 | Reception,Nurse | Clinic | Backend | Must | MVP | 8 | 13 |  |  | NB-152 | Ledger reconciles; concurrent redemption cannot over-consume | Done
NB-154 | E14 Treatment Packages | Packages | Session redemption booking & counter rules | Booking leaves the count unchanged; it decrements only on completed attendance. | PKG-10 | Nurse,Reception,Patient | Clinic | Fullstack | Must | MVP | 5 | 14 |  |  | NB-153, NB-090 | A booked-but-not-attended session does not decrement the counter | Done
NB-155 | E14 Treatment Packages | Packages | Doctor-restricted package eligibility | A package restricted to a named doctor is affected when that doctor is blocked or on leave. | PKG-02,DOC-03 | Reception | Clinic | Backend | Must | MVP | 5 | 14 |  |  | NB-153, NB-091 | Blocking a doctor warns about active packages restricted to them | Done
NB-156 | E14 Treatment Packages | Packages | Payment plans at sale & instalment auto-collection | Instalment schedules created at sale with automatic collection. | PKG-06,PKG-07 | Reception,Owner | Clinic | Fullstack | Should | Phase 2 | 8 | 17 |  |  | NB-152, NB-168 | Failed instalment retries on a defined ladder and never double-charges | Not started
NB-157 | E14 Treatment Packages | Packages | Expiry ladder, grace period & extension | 30/14/7-day warnings, grace handling and owner-approved extensions. | PKG-13 | Owner,Patient | Clinic | Fullstack | Must | MVP | 5 | 15 |  |  | NB-153, NB-308 | Expiry job idempotent; extension requires approval and is audited | Done
NB-158 | E14 Treatment Packages | Packages | Progress view & next-session nudges | Patient-visible progress with automatic pre-session reminders. | PKG-12 | Patient,Reception | Patient | Fullstack | Must | MVP | 5 | 15 |  |  | NB-153, NB-197 | Progress and next session are visible in the patient channel | Done
NB-159 | E14 Treatment Packages | Packages | Transfer & gifting of remaining sessions | One transfer maximum, with the receiving party's consent. | PKG-16 | Reception,Patient | Clinic | Fullstack | Could | Phase 2 | 5 | 18 |  |  | NB-153 | A second transfer of the same instance is refused | Not started
NB-160 | E14 Treatment Packages | Packages | Package refunds & pro-rata calculation | Refund on unconsumed sessions with correct tax reversal. |  | Owner | Clinic | Fullstack | Must | MVP | 8 | 15 |  |  | NB-153, NB-166 | Refund and tax reversal verified against finance test cases | Done
NB-161 | E14 Treatment Packages | Packages | Package liability & revenue recognition | Sales, redemption, deferred versus recognised revenue and outstanding liability. | PKG-17,PKG-18,OWN-08 | Owner | Clinic | Fullstack | Must | MVP | 8 | 16 |  |  | NB-153, NB-228 | Liability ties to the billing ledger to the paisa/halala | Done
NB-162 | E15 Billing, Tax & Payments | Billing | Checkout & invoice generation | Line items, quantity, discounts, per-line tax and totals. |  | Reception | Clinic | Fullstack | Must | MVP | 13 | 10 |  |  | NB-061, NB-094 | Invoice totals match the wireframe calculations exactly | Done
NB-163 | E15 Billing, Tax & Payments | Billing | India GST engine | CGST/SGST/IGST split, HSN/SAC codes, exempt clinical services and GST invoice format. | SYS-09 | Reception,Owner | Clinic | Backend | Must | MVP | 8 | 11 |  |  | NB-162 | Validated against sample GST returns by a tax reviewer | Not started
NB-164 | E15 Billing, Tax & Payments | Billing | Saudi VAT & ZATCA e-invoicing | 15% VAT, zero-rated cases, QR code, XML invoice and Phase-2 clearance integration. | SYS-09 | Reception,Owner | Clinic | Backend | Must | MVP | 13 | 12 |  |  | NB-162 | Passes the ZATCA compliance validator in sandbox | Not started
NB-165 | E15 Billing, Tax & Payments | Billing | Discounts, write-offs & approval thresholds | Permission-gated, with maker-checker above a configurable limit. | SYS-06 | Reception,Owner | Clinic | Fullstack | Must | MVP | 5 | 12 |  |  | NB-162, NB-056 | Staff without discount rights cannot apply one via the API either | Not started
NB-166 | E15 Billing, Tax & Payments | Billing | Refunds, credit notes & cancellations | Full and partial with tax reversal and a link to the original invoice. |  | Owner | Clinic | Fullstack | Must | MVP | 8 | 14 |  |  | NB-162, NB-163, NB-164 | Credit note references the original; the ledger balances | Not started
NB-167 | E15 Billing, Tax & Payments | Billing | Payment capture — cash, card, UPI, Mada, wallets | Region-specific methods with split payment support. |  | Reception | Clinic | Fullstack | Must | MVP | 8 | 13 |  |  | NB-162 | Split payments across methods reconcile to the invoice total | Not started
NB-168 | E15 Billing, Tax & Payments | Billing | Payment gateway integration | Tokenised, PCI-DSS SAQ-A scope, webhook reconciliation, idempotent capture. |  | Reception | Clinic | Integration | Must | MVP | 8 | 14 |  |  | NB-167 | No card data touches Nabd servers; a duplicate webhook is a no-op | Not started
NB-169 | E15 Billing, Tax & Payments | Billing | Prepaid payment links & desk QR collection | Prepaid link sent to the patient; the existing desk-counter QR collection path is left untouched. | RCP-08,PAT-10 | Reception,Patient | Clinic | Fullstack | Must | MVP | 5 | 15 |  |  | NB-168, NB-197 | Link is prepaid-only; desk QR flow is unchanged and still reconciles | Not started
NB-170 | E15 Billing, Tax & Payments | Billing | Price transparency & estimates | A priced estimate sent over WhatsApp that converts to a bill in one tap. | BIL-07 | Reception,Patient | Clinic | Fullstack | Must | MVP | 8 | 15 |  |  | NB-061, NB-197 | Estimate converts to an invoice without re-entry and the quoted price is honoured | Not started
NB-171 | E15 Billing, Tax & Payments | Billing | Dues list & automatic follow-up | Age in days with an automatic reminder that stops the moment payment lands. | BIL-06 | Reception,Owner | Clinic | Fullstack | Must | MVP | 5 | 15 |  |  | NB-162, NB-308 | Reminder stops on payment with no lag; ageing matches the ledger | Not started
NB-172 | E15 Billing, Tax & Payments | Billing | Day close & cash reconciliation | Counter-wise collection, expected versus counted, variance reason and day lock. | OWN-07 | Owner | Clinic | Fullstack | Must | MVP | 8 | 14 |  |  | NB-167 | A closed day is immutable; reopening requires owner approval and is audited | Not started
NB-173 | E15 Billing, Tax & Payments | Billing | End-of-day desk summary | Reception's own close-of-day summary, derived from the same billing source as day close. | RCP-12 | Reception | Clinic | Fullstack | Should | MVP | 5 | 16 |  |  | NB-172 | Figures derive from the same source view as day close and cannot diverge | Not started
NB-174 | E15 Billing, Tax & Payments | Billing | Invoice printing, PDF & secure sharing | Thermal and A4 layouts in all three languages, delivered via the secure link path. | SYS-18 | Reception | Clinic | Fullstack | Must | MVP | 5 | 15 |  |  | NB-162, NB-076 | Arabic invoice prints RTL correctly on both layouts | Not started
NB-175 | E15 Billing, Tax & Payments | Billing | Simple insurance claim export | A claim pack assembled in under two minutes, requiring a valid licence number. Full claims via certified middleware are explicitly Phase 3 and Ayushman is out of scope. | BIL-11,SYS-10,CMP-11 | Owner,Reception | Clinic | Fullstack | Should | MVP | 8 | 17 |  |  | NB-162, NB-070 | Claim pack builds in under two minutes; blocked with a clear reason when the licence has expired | Not started
NB-176 | E15 Billing, Tax & Payments | Billing | NPHIES eligibility-check-lite | One-click coverage check shown on the patient row before billing. No live claim pipeline here. | RCP-07,SYS-10 | Reception | Clinic | Integration | Should | Phase 2 | 8 | 19 |  |  | NB-162, NB-070 | Coverage result appears on the patient row before billing; no claim is submitted | Not started
NB-177 | E16 Pharmacy | Pharmacy | Pharmacy mode configuration — external, hybrid, in-house | Three modes with a published capability matrix; hybrid and in-house are paid tiers. | CAD-11 | Owner | Clinic | Fullstack | Must | MVP | 8 | 16 |  |  | NB-008, NB-061 | Mode switch changes available capability exactly per the rules grid; downgrade makes the item master read-only with no new dispensing | Done
NB-178 | E16 Pharmacy | Pharmacy | Small-shelf item master | An item creatable in under a minute for clinics with a small shelf. | PHR-12 | Reception,Owner | Clinic | Fullstack | Must | MVP | 5 | 16 |  |  | NB-177 | New item created in under a minute; becomes read-only when the mode is downgraded | Done
NB-179 | E16 Pharmacy | Pharmacy | e-Rx dispensing queue | A prescription appears in the dispensing queue within five seconds of consultation close, visible from billing. | PHR-01 | Reception | Clinic | Fullstack | Must | MVP | 8 | 17 |  |  | NB-177, NB-109 | Prescription reaches the queue within five seconds of consultation close | Done
NB-180 | E16 Pharmacy | Pharmacy | One-tap dispense & bill via the Consumable category | Dispensing raises a Consumable line on the single patient bill and decrements stock in one action. | PHR-06,PHR-09 | Reception | Clinic | Fullstack | Must | MVP | 8 | 17 |  |  | NB-178, NB-162 | One bill, one tap, stock decremented atomically | Done
NB-181 | E16 Pharmacy | Pharmacy | Full inventory with batch & expiry, FEFO suggestion | Every batch carries a number and expiry; earliest-expiry-first is suggested by default. | PHR-03 | Reception,Owner | Clinic | Fullstack | Must | Phase 2 | 8 | 18 |  |  | NB-178 | FEFO suggested by default; overriding it requires an explicit action | Not started
NB-182 | E16 Pharmacy | Pharmacy | Controlled-drug register | Warning plus register entry — deliberately no hard block, since no registered pharmacist licence is assumed. | PHR-04,CEO-27 | Reception,Owner | Clinic | Fullstack | Must | Phase 2 | 8 | 18 |  |  | NB-178, NB-111 | Warning shown and register entry written; dispensing is not hard-blocked | Not started
NB-183 | E16 Pharmacy | Pharmacy | Low-stock & expiry alerts to a named person | Alerts go to one named person, never a mailing list. | PHR-10 | Owner | Clinic | Fullstack | Should | Phase 2 | 5 | 19 |  |  | NB-181, NB-308 | Alert recipient is a single named user; thresholds configurable | Not started
NB-184 | E16 Pharmacy | Pharmacy | WhatsApp refill reminders | Timing derived from the dispensed quantity. A controlled item is barred from self-serve refill. | PHR-05 | Patient | Patient | Fullstack | Should | Phase 2 | 5 | 19 |  |  | NB-179, NB-197 | Refill timing derives from dispensed quantity; controlled items cannot self-refill | Not started
NB-185 | E16 Pharmacy | Pharmacy | Bought-where adherence capture | Asked at pre-consult in every mode. Capture only, consent-worded for this purpose, never monetised. | PHR-11,CEO-25 | Doctor,Nurse | Clinic | Fullstack | Should | MVP | 5 | 17 |  |  | NB-102, NB-242 | Consent wording is purpose-specific; the data has no commercial export path | Not started
NB-186 | E16 Pharmacy | Pharmacy | Over-the-counter sale without a patient record | A counter sale creates neither a patient record nor a token. | PHR-12 | Reception | Clinic | Fullstack | Could | Phase 2 | 5 | 20 |  |  | NB-180 | OTC sale produces an invoice with no patient record or token created | Done
NB-187 | E16 Pharmacy | Pharmacy | Pharmacy stock reporting & valuation | Stock on hand, movement, expiry write-off and valuation. | PHR-03,PHR-10 | Owner | Clinic | Fullstack | Could | Phase 3 | 5 | 21 |  |  | NB-181, NB-228 | Valuation reconciles with purchase and dispense history | Not started
NB-188 | E17 Messaging Platform & WhatsApp Infrastructure | Messaging | Managed WhatsApp Business onboarding (SYS-25) | The clinic never touches Meta Business Manager. Nabd completes Meta verification on the clinic's behalf as a fully managed service. | SYS-25,CAD-07,SSA-03 | Owner,Platform | Patient | Integration | Must | MVP | 13 | 9 |  |  | NB-007, NB-261 | A clinic goes live on WhatsApp without ever opening Meta Business Manager | Not started
NB-189 | E17 Messaging Platform & WhatsApp Infrastructure | Messaging | Shared trial number to owned number migration | Shared number on trial, the clinic's own number once paid, migrating without losing conversation history. | SSA-03,CAD-07 | Platform,Owner | Patient | Integration | Must | MVP | 8 | 12 |  |  | NB-188 | Migration preserves history and in-flight conversations | Not started
NB-190 | E17 Messaging Platform & WhatsApp Infrastructure | Messaging | Template library, approval state & quality rating | Template registration, approval tracking and per-number quality monitoring. | CAD-07,SSA-03 | Owner,Platform | Patient | Integration | Must | MVP | 8 | 10 |  |  | NB-188 | Rejected templates surface to the clinic with the reason and a fix path | Not started
NB-191 | E17 Messaging Platform & WhatsApp Infrastructure | Messaging | Variable-fill-only template enforcement | Fixed template text is not editable anywhere in the product; only variable slots accept input. | CMP-07 | Reception | Patient | Fullstack | Must | MVP | 5 | 10 |  |  | NB-190, NB-018 | Fixed text is physically uneditable in every send path, including the API | Not started
NB-192 | E17 Messaging Platform & WhatsApp Infrastructure | Messaging | 24-hour session window governance | Composer accepts free text only while the window is open; a closing-soon countdown then an expired state that permits approved templates only. |  | Reception,Nurse | Patient | Fullstack | Must | MVP | 5 | 11 |  |  | NB-018, NB-190 | Free text is refused once the window expires; countdown is accurate to the second | Not started
NB-193 | E17 Messaging Platform & WhatsApp Infrastructure | Messaging | Delivery-state tracking & SMS fallback | Queued, delivered, read, failed, SMS fallback queued and blocked. Fallback fires automatically on failure. | SYS-01 | Reception,Platform | Patient | Integration | Must | MVP | 8 | 11 |  |  | NB-188, NB-007 | Failure triggers SMS fallback automatically and the state is visible per message | Not started
NB-194 | E17 Messaging Platform & WhatsApp Infrastructure | Messaging | India DLT registration & messaging compliance | India-specific DLT template registration, entirely absent for KSA tenants. | CMP-07 | Owner,Platform | Patient | Integration | Must | MVP | 8 | 13 |  |  | NB-190 | DLT-compliant templates registered; the whole surface is absent for KSA tenants | Not started
NB-195 | E17 Messaging Platform & WhatsApp Infrastructure | Messaging | Prayer-window send reconciliation | Routine sends defer around prayer windows; operationally urgent broadcasts such as doctor delay are not held. | SYS-03 | Patient,Reception | Patient | Backend | Must | MVP | 5 | 12 |  |  | NB-193 | Routine reminder defers past the window; a delay broadcast sends immediately | Not started
NB-196 | E17 Messaging Platform & WhatsApp Infrastructure | Messaging | Consent gate on every outbound send | Consent is enforced at send time and takes effect across every surface in under a minute. | SYS-02,CMP-02,NFR-08 | All | Shared | Backend | Must | MVP | 8 | 11 |  |  | NB-053, NB-193 | Withdrawing consent suppresses an already-queued reminder within one minute | Not started
NB-197 | E17 Messaging Platform & WhatsApp Infrastructure | Messaging | Shared clinic WhatsApp inbox with canned replies | Reception's shared inbox with conversation list, ageing chips, unread counts and canned replies. | RCP-11 | Reception | Clinic | Fullstack | Must | MVP | 13 | 13 |  |  | NB-018, NB-192, NB-193 | Conversations age visibly past the threshold; canned replies respect the session window | Not started
NB-198 | E17 Messaging Platform & WhatsApp Infrastructure | Messaging | Clinic-branded personal messaging | Messages carry the clinic's identity rather than a generic platform identity. | PAT-17 | Patient | Patient | Fullstack | Must | MVP | 5 | 12 |  |  | NB-188 | Clinic name and branding appear on the patient's device | Not started
NB-199 | E17 Messaging Platform & WhatsApp Infrastructure | Messaging | Campaign engine with child & consent pre-checks | Campaign sends pre-filtered against child profiles and consent state before dispatch. | DPO-09,CMP-04,SYS-02 | Owner | Patient | Backend | Must | MVP | 5 | 14 |  |  | NB-196 | A campaign cannot dispatch to a child profile or a withdrawn consent | Not started
NB-200 | E17 Messaging Platform & WhatsApp Infrastructure | Messaging | Messaging concurrency & provider capacity model | Patient-side concurrency is unbounded and each conversation is stateless; the real ceiling is provider capacity (80 msg/s per verified number, 1000 conversations/24h). | NFR-02 | Platform | Patient | Backend | Must | MVP | 8 | 16 |  |  | NB-193 | Load test confirms stateless scaling; provider rate limits are respected with backpressure, not message loss | Not started
NB-201 | E18 Patient WhatsApp Surface | Patient | WhatsApp zero-form registration | A patient registers entirely in chat with no form to fill. | PAT-01 | Patient | Patient | Fullstack | Must | MVP | 8 | 13 |  |  | NB-197, NB-071 | Registration completes in chat with no web form and no app install | Not started
NB-202 | E18 Patient WhatsApp Surface | Patient | Guided booking within a six-tap budget | The booking journey is explicitly tap-budgeted. | PAT-03 | Patient | Patient | Fullstack | Must | MVP | 13 | 14 |  |  | NB-201, NB-090 | Booking completes within the stated tap budget on a single-member number | Not started
NB-203 | E18 Patient WhatsApp Surface | Patient | Layered reminders with confirmation cascade | Staged reminders that escalate only when unconfirmed. | PAT-04 | Patient | Patient | Fullstack | Must | MVP | 8 | 14 |  |  | NB-202, NB-196 | Confirmation stops the cascade immediately; no duplicate reminder is sent | Not started
NB-204 | E18 Patient WhatsApp Surface | Patient | Live queue & your-turn tracking | The patient follows their position and estimated turn from chat. | PAT-05 | Patient | Patient | Fullstack | Must | MVP | 8 | 15 |  |  | NB-202, NB-096 | Position updates track the clinic queue within the sync budget | Not started
NB-205 | E18 Patient WhatsApp Surface | Patient | Cancel with one-tap reason | Cancellation captures a reason from the shared reason list in one tap. | PAT-06,SYS-07 | Patient | Patient | Fullstack | Must | MVP | 5 | 15 |  |  | NB-202, NB-011 | Reason captured in one tap; the slot releases immediately | Not started
NB-206 | E18 Patient WhatsApp Surface | Patient | One-tap reschedule | Rescheduling without leaving the conversation. | PAT-08 | Patient | Patient | Fullstack | Must | MVP | 5 | 15 |  |  | NB-202 | Reschedule respects the same availability rules as reception booking | Not started
NB-207 | E18 Patient WhatsApp Surface | Patient | Arrival check-in — QR or in-chat | The patient checks in by scanning at the desk or from the conversation. | PAT-09 | Patient | Patient | Fullstack | Must | MVP | 5 | 16 |  |  | NB-202, NB-094 | Both paths produce the same queue state transition | Not started
NB-208 | E18 Patient WhatsApp Surface | Patient | Waitlist join & auto-fill offer acceptance | The patient joins a waitlist and accepts a freed slot within the offer window. | PAT-07 | Patient | Patient | Fullstack | Should | MVP | 5 | 16 |  |  | NB-099, NB-202 | Offer acceptance after expiry is refused cleanly | Not started
NB-209 | E18 Patient WhatsApp Surface | Patient | Payments, deposits & refunds in chat | In-conversation payment, deposit and refund handling. | PAT-10 | Patient | Patient | Fullstack | Must | MVP | 8 | 16 |  |  | NB-168, NB-197 | Payment in chat reconciles to the same invoice as a desk payment | Not started
NB-210 | E18 Patient WhatsApp Surface | Patient | Buy a package in WhatsApp | Package purchase completed in conversation, with the tax-correct invoice delivered in-thread. | PAT-21,PKG-04,SYS-09 | Patient | Patient | Fullstack | Should | Phase 2 | 8 | 18 |  |  | NB-209, NB-152 | GST or ZATCA invoice delivered in-thread with the correct refund-policy text | Not started
NB-211 | E18 Patient WhatsApp Surface | Patient | Package session tracking for the patient | Remaining sessions, validity and next appointment visible in chat. | PAT-22,PKG-12 | Patient | Patient | Fullstack | Should | MVP | 5 | 17 |  |  | NB-153, NB-201 | Counts match the clinic-side ledger exactly | Not started
NB-212 | E18 Patient WhatsApp Surface | Patient | Post-visit follow-up check-ins | A day-after check-in that routes an unwell reply to the clinic. | PAT-11 | Patient | Patient | Fullstack | Should | MVP | 5 | 17 |  |  | NB-144, NB-196 | A not-well reply escalates to the clinical triage inbox, not reception | Not started
NB-213 | E18 Patient WhatsApp Surface | Patient | Receive prescriptions & reports securely | Documents delivered as expiring links, never posted inline. | PAT-13,SYS-18 | Patient | Patient | Fullstack | Must | MVP | 5 | 17 |  |  | NB-076, NB-201 | No document is ever posted into open chat; every access is logged | Not started
NB-214 | E18 Patient WhatsApp Surface | Patient | My data & privacy self-service | The patient-facing privacy menu — request data, correct data, withdraw consent. | PAT-14,CMP-03 | Patient | Patient | Fullstack | Must | MVP | 8 | 18 |  |  | NB-243, NB-201 | Requests raise a tracked case with the statutory timer; the menu itself gates Phase 2 items | Not started
NB-215 | E18 Patient WhatsApp Surface | Patient | Multilingual patient interaction | English, Hindi, Hinglish, Tamil, Malayalam, Kannada, Bengali and Arabic in the patient channel. | PAT-15 | Patient | Patient | Fullstack | Must | MVP | 8 | 17 |  |  | NB-201, NB-030 | Language switch persists per patient and applies to templates and free text | Not started
NB-216 | E18 Patient WhatsApp Surface | Patient | Treatment-linked recall in the patient channel | Recall messages generated by the clinical recall engine reach the patient with the right timing. | PAT-20 | Patient | Patient | Fullstack | Must | MVP | 5 | 18 |  |  | NB-116, NB-196 | Recall arrives on schedule and stops when the appointment is booked | Not started
NB-217 | E18 Patient WhatsApp Surface | Patient | Google-review prompt | A post-visit review prompt that never gates or filters reviews. | PAT-26,CEO-14 | Patient | Patient | Fullstack | Should | Phase 2 | 3 | 19 |  |  | NB-212 | No filtering or gating logic exists; the prompt sends patients to Google ungated | Not started
NB-218 | E18 Patient WhatsApp Surface | Patient | Referral rewards | Patient referral with reward tracking. | PAT-25 | Patient | Patient | Fullstack | Could | Phase 2 | 5 | 20 |  |  | NB-201 | Reward attribution is auditable and cannot be self-referred | Not started
NB-219 | E18 Patient WhatsApp Surface | Patient | Family & chronic-care memberships | A booking and check-in convenience plan, explicitly not a clinical care contract. | PAT-24,CEO-15,CGV-10 | Patient | Patient | Fullstack | Could | Phase 3 | 8 | 21 |  |  | NB-088 | Product copy never implies clinical care obligations; legal review sign-off obtained | Not started
NB-220 | E18 Patient WhatsApp Surface | Patient | Teleconsultation booking & join | Booked as a visit type with a partner deep-link. Explicitly a Phase 3 partner integration. | PAT-16 | Patient,Doctor | Patient | Integration | Could | Phase 3 | 8 | 22 |  |  | NB-202 | Booked as a visit type; the join path is a partner deep-link, not a built video stack | Not started
NB-221 | E19 Aggregator & Demand | Aggregator | Unified Nabd number & invisible routing | One shared number routes a patient to the right clinic without the patient choosing infrastructure. | AGG-01 | Patient | Patient | Fullstack | Should | Phase 2 | 13 | 18 |  |  | NB-188, NB-202 | A patient reaching the shared number lands with the right clinic without naming it | Not started
NB-222 | E19 Aggregator & Demand | Aggregator | Emergency phrase interception | Emergency phrases stop the flow and direct the patient to 108 (India) or 997 (KSA). No clinic is suggested. | AGG-02,CEO-14 | Patient | Patient | Backend | Must | Phase 2 | 8 | 18 |  |  | NB-221 | Emergency phrases in every supported language halt routing and show emergency guidance only | Not started
NB-223 | E19 Aggregator & Demand | Aggregator | Word-to-specialty matching | Keyword matching to a specialty only — no clinical interpretation and no triage. Unmatched requests go to the nearest clinic's reception. | AGG-03 | Patient | Patient | Backend | Should | Phase 2 | 8 | 19 |  |  | NB-221, NB-222 | No symptom interpretation occurs; unmatched input routes to reception rather than guessing | Not started
NB-224 | E19 Aggregator & Demand | Aggregator | Clinic discovery, distance & slot surfacing | Nearby clinics with distance, next slot, price band, insurance and doctor-availability flags. | AGG-01 | Patient | Patient | Fullstack | Should | Phase 2 | 8 | 19 |  |  | NB-221, NB-090 | Results are ordered by a stated rule; no paid placement is possible | Not started
NB-225 | E19 Aggregator & Demand | Aggregator | Verified-visit rating system | A rating comes only from a completed, paid visit on the platform. Hidden until ten ratings, then shown as New on Nabd. | AGG-05,CEO-14 | Patient | Patient | Backend | Should | Phase 2 | 8 | 20 |  |  | NB-224, NB-172 | A rating cannot be created without a completed paid visit; fewer than ten ratings shows New on Nabd | Not started
NB-226 | E19 Aggregator & Demand | Aggregator | Separate Nabd and Google rating display | The verified Nabd score and the Google rating are shown separately and never blended into one number. | AGG-05,CEO-14,PAT-26 | Patient | Patient | Frontend | Should | Phase 2 | 3 | 20 |  |  | NB-225 | The two scores are never averaged or combined anywhere in the product | Not started
NB-227 | E19 Aggregator & Demand | Aggregator | Coverage versus demand analytics | Patient demand on the unified number against actual clinic coverage — the sales signal for territory expansion. | AGG-04 | Platform | Platform | Fullstack | Should | Phase 2 | 8 | 20 |  |  | NB-221, NB-270 | Unserved demand by territory is reportable and feeds the sales pipeline | Not started
NB-228 | E20 Owner Insights & Reports | Reports | Reporting read model & nightly aggregation | Reports never touch the operational database. |  | Owner | Clinic | Backend | Must | MVP | 8 | 13 |  |  | NB-003, NB-007 | Every report reads exclusively from the read model | Not started
NB-229 | E20 Owner Insights & Reports | Reports | Daily money dashboard | The owner's today view, opening in under two seconds on mobile. | OWN-01 | Owner | Clinic | Fullstack | Must | MVP | 5 | 15 |  |  | NB-228, NB-025 | Opens in under two seconds on a mid-range mobile device | Done
NB-230 | E20 Owner Insights & Reports | Reports | Where patients come from | One source tag per visit, never a dual axis. | OWN-02,MKT-04 | Owner | Clinic | Fullstack | Must | MVP | 5 | 16 |  |  | NB-228, NB-079 | Single-axis source attribution; no dual-axis chart is produced | Done
NB-231 | E20 Owner Insights & Reports | Reports | Staff collection & performance | Coaching data for a small team, not surveillance. A staff member sees only their own row. | OWN-04 | Owner | Clinic | Fullstack | Should | MVP | 5 | 16 |  |  | NB-228, NB-051 | A staff member can see only their own row; the access rule is stated on the surface | Done
NB-232 | E20 Owner Insights & Reports | Reports | Package liability reporting | Sales, redemption and revenue recognition for packages. | PKG-18,OWN-08,PKG-17 | Owner | Clinic | Fullstack | Must | MVP | 5 | 16 |  |  | NB-161 | Figures tie to the package ledger | Done
NB-233 | E20 Owner Insights & Reports | Reports | Billing leakage alerts | An alert list with a configurable threshold, always visible. | OWN-09,BIL-06 | Owner | Clinic | Fullstack | Must | MVP | 8 | 17 |  |  | NB-228, NB-171 | Threshold configurable; untagged and unbilled visits surface as alerts | Done
NB-234 | E20 Owner Insights & Reports | Reports | Repeat-patient & recall value | Aggregated retention reporting only — no individual patient list. | OWN-03,OWN-05 | Owner | Clinic | Fullstack | Should | Phase 2 | 5 | 18 |  |  | NB-228 | No individual patient list is exposed anywhere in this view | Done
NB-235 | E20 Owner Insights & Reports | Reports | Rule-based no-show prediction | A transparent rule-based signal, not an opaque model. | OWN-05 | Owner,Reception | Clinic | Fullstack | Could | Phase 2 | 5 | 19 |  |  | NB-228 | The rule is stated on the surface and is auditable | Done
NB-236 | E20 Owner Insights & Reports | Reports | Doctor punctuality statistic | Owner-only aggregate of delay events, average declared minutes and same-day repeats. No per-patient log; neither doctor nor reception can see it. | RCP-04 | Owner | Clinic | Fullstack | Should | MVP | 5 | 17 |  |  | NB-100, NB-228 | Absent for doctor and reception roles; the access rule is printed on the surface | Done
NB-237 | E20 Owner Insights & Reports | Reports | Scheduled report delivery & export | CSV and PDF export plus emailed schedules, watermarked and access-logged. | SYS-23 | Owner | Clinic | Fullstack | Could | Phase 2 | 3 | 19 |  |  | NB-228, NB-027 | Every export writes an audit event with row counts | In progress
NB-238 | E21 Compliance, Consent & Data Protection | Compliance | Immutable audit trail service | Who, what, when and before/after for every PHI and financial action, append-only. | SYS-13 | All | Shared | Backend | Must | MVP | 8 | 7 |  |  | NB-003 | Tamper attempt detected; audit survives application-level deletion | Done
NB-239 | E21 Compliance, Consent & Data Protection | Compliance | Audit log surface for the clinic | Owner-facing searchable audit view with export. | SYS-13,CAD-07 | Owner | Clinic | Frontend | Must | MVP | 5 | 14 |  |  | NB-238 | Searchable by user, patient, date and action; export is itself audited | Not started
NB-240 | E21 Compliance, Consent & Data Protection | Compliance | Consent & notice template library | A new tenant goes live with correct market templates without writing anything. | CMP-01,CAD-08 | Owner,Platform | Shared | Fullstack | Must | MVP | 8 | 10 |  |  | NB-003, NB-261 | A newly provisioned tenant has correct market templates on day one | Not started
NB-241 | E21 Compliance, Consent & Data Protection | Compliance | Consent as a hard gate with owner evidence | Consent blocks the action, not just the UI, and the owner can evidence it. | CMP-02,NFR-08 | Owner | Shared | Fullstack | Must | MVP | 8 | 13 |  |  | NB-053, NB-240 | Sending is blocked on every channel when consent is absent; the owner can produce evidence | Not started
NB-242 | E21 Compliance, Consent & Data Protection | Compliance | Consent registry & versioned audit | Every consent version recorded, including signed DPA versions. | DPO-01,CEO-17 | Owner,Platform | Shared | Backend | Must | MVP | 8 | 13 |  |  | NB-240, NB-238 | Every consent and DPA version is retrievable with its timestamp | Not started
NB-243 | E21 Compliance, Consent & Data Protection | Compliance | Patient rights self-service & request queue | Patient-initiated rights requests landing in a tracked clinic queue. | CMP-03,PAT-14 | Owner,Patient | Shared | Fullstack | Must | MVP | 8 | 15 |  |  | NB-242 | A request raises a tracked case visible to the clinic and the DPO | Not started
NB-244 | E21 Compliance, Consent & Data Protection | Compliance | DSR workflow engine with statutory timers | A tracked case with a 90-day DPDP timer for India and a closure letter on completion. | DPO-02,CMP-03,NFR-07 | Owner,Platform | Shared | Fullstack | Must | MVP | 8 | 16 |  |  | NB-243, NB-308 | Timer runs to the correct statutory deadline per region; closure letter generated automatically | Not started
NB-245 | E21 Compliance, Consent & Data Protection | Compliance | Retention auto-rules with pre-delete notice | Default schedules active from day one with no setup, plus a pre-delete notice. The full policy engine is Phase 2. | CMP-05,DPO-05 | Owner | Shared | Backend | Must | MVP | 8 | 15 |  |  | NB-255, NB-308 | Defaults are active on day one; nothing is deleted without prior notice | Not started
NB-246 | E21 Compliance, Consent & Data Protection | Compliance | Retention & deletion policy engine | The configurable policy engine behind the defaults. | DPO-05 | Owner,Platform | Shared | Backend | Should | Phase 2 | 8 | 20 |  |  | NB-245 | Policies are configurable per data class and never override a legal hold | Not started
NB-247 | E21 Compliance, Consent & Data Protection | Compliance | Medical record retention & legal hold | Region-specific retention clocks with legal hold overriding erasure. | NFR-07,DPO-05 | Owner | Shared | Backend | Must | MVP | 5 | 16 |  |  | NB-245 | The retention job never deletes a record under legal hold; 3-year export retention honoured | Not started
NB-248 | E21 Compliance, Consent & Data Protection | Compliance | Breach-notification runbook & clinic-facing ops | Severity assessment and the regulatory notification workflow, exposed to the clinic. | CMP-06 | Owner | Shared | Compliance | Must | MVP | 5 | 17 |  |  | NB-293 | Runbook exercised in a tabletop; notification deadlines documented per region | Not started
NB-249 | E21 Compliance, Consent & Data Protection | Compliance | Platform breach management operations | The platform-side incident and breach operations console. | DPO-03,SSA-05 | Platform | Platform | Fullstack | Must | MVP | 5 | 18 |  |  | NB-248, NB-265 | Every breach case is tracked with owner, clock and regulator status | Not started
NB-250 | E21 Compliance, Consent & Data Protection | Compliance | Licence & credential expiry tracker | Manual date entry with no verification integration in this release. An expired clinician disappears from online booking until renewed. | CMP-11,PAT-03,DOC-03 | Owner | Clinic | Fullstack | Must | MVP | 8 | 14 |  |  | NB-070, NB-091 | An expired licence removes the clinician from online booking and blocks the claim pack | Not started
NB-251 | E21 Compliance, Consent & Data Protection | Compliance | Compliance health card & grievance officer setup | One traffic-light card with no legal jargon, plus grievance officer configuration. | CMP-12 | Owner | Clinic | Frontend | Should | Phase 2 | 5 | 19 |  |  | NB-250, NB-244 | A non-lawyer owner can read their compliance position at a glance | Not started
NB-252 | E21 Compliance, Consent & Data Protection | Compliance | Child-data protection controls | Child protection flag propagated to every module, mirrored platform-side. | DPO-09,CMP-04 | All | Shared | Backend | Must | MVP | 5 | 14 |  |  | NB-053 | The flag is enforced in every module, not only in messaging | Not started
NB-253 | E21 Compliance, Consent & Data Protection | Compliance | India DPDP Act 2023 compliance pack | Consent, notice, data-principal rights, grievance officer and breach reporting. | CMP-03,DPO-02,NFR-07 | Owner,Platform | Shared | Compliance | Must | MVP | 8 | 17 |  |  | NB-244, NB-242 | Legal review sign-off for India | Not started
NB-254 | E21 Compliance, Consent & Data Protection | Compliance | Saudi PDPL & SDAIA compliance pack | Residency, controller obligations, cross-border rules and retention. | NFR-04,SYS-14 | Owner,Platform | Shared | Compliance | Must | MVP | 8 | 17 |  |  | NB-271, NB-242 | Legal review sign-off for KSA; region lock evidenced | Not started
NB-255 | E21 Compliance, Consent & Data Protection | Compliance | Data classification & handling standard | PHI, PII, financial and operational tiers with handling rules per tier. |  | All | Shared | Compliance | Must | MVP | 3 | 6 |  |  | NB-003 | Every table and log field is classified | Not started
NB-256 | E21 Compliance, Consent & Data Protection | Compliance | Regulatory watch | Tracking regulatory change across both markets and routing it into the backlog. | SSA-11 | Platform | Platform | Compliance | Should | Phase 2 | 5 | 20 |  |  | NB-272 | A regulatory change produces a tracked backlog item with an owner and a deadline | Not started
NB-257 | E22 Platform Console — SaaS Operations | Platform | Seven SaaS operator roles | Super admin, Implementation, Support engineer, Billing, SRE, Commercial read-only and Compliance/DPO. No single super-admin does everything. | SSA-02 | Platform | Platform | Backend | Must | MVP | 8 | 6 |  |  | NB-050, NB-017 | Each role sees only its own navigation; create buttons do not exist for roles without create rights | Done
NB-258 | E22 Platform Console — SaaS Operations | Platform | Provisioning as a job queue, not a wizard | A provisioning job is an object with six steps: create tenant, migrate schema, seed masters, provision WhatsApp, verify and invite owner, go live. | SSA-01,SYS-21 | Platform | Platform | Backend | Must | MVP | 13 | 7 |  |  | NB-002, NB-257 | A job is resumable and inspectable at every step; state is queued/running/done/failed/rolled back | Done
NB-259 | E22 Platform Console — SaaS Operations | Platform | Provisioning failure & automatic rollback | A failed step rolls back cleanly with no half-created tenant, and the error is stated plainly. | SSA-01 | Platform | Platform | Backend | Must | MVP | 8 | 10 |  |  | NB-258 | A region-mismatch failure rolls back with no tenant created and a readable error | Done
NB-260 | E22 Platform Console — SaaS Operations | Platform | Self-serve versus enterprise provisioning paths | Both paths run through the same job engine with different approval gates. | SSA-01,SCS-01 | Platform | Platform | Backend | Must | MVP | 5 | 10 |  |  | NB-258 | Both paths produce identical tenant state; only the gates differ | Done
NB-261 | E22 Platform Console — SaaS Operations | Platform | Tenant lifecycle — seven audited states | Trialing through to offboarded, with every transition audited. | DPO-04,SSA-01 | Platform | Platform | Backend | Must | MVP | 5 | 7 |  |  | NB-258 | All seven states implemented; every transition writes an audit event | Done
NB-262 | E22 Platform Console — SaaS Operations | Platform | Clinic fleet console | Health, usage, plan, region and incident flags across every tenant. | SSA-01,SSA-06 | Platform | Platform | Frontend | Must | MVP | 8 | 12 |  |  | NB-261, NB-257 | Fleet view loads 500 tenants in under two seconds | Done
NB-263 | E22 Platform Console — SaaS Operations | Platform | Platform health monitoring | Sync backlog, WhatsApp quality and error rate per clinic. A sync queue means a clinic working offline, not lost data. | SSA-06,SYS-22,NFR-12 | Platform | Platform | Fullstack | Must | MVP | 8 | 13 |  |  | NB-262, NB-304 | Quality under 60% raises a sending-at-risk alert; a sync backlog is not reported as data loss | Not started
NB-264 | E22 Platform Console — SaaS Operations | Platform | WABA fleet quality monitoring | Per-number quality, template approval state and messaging capacity across the fleet. | SSA-03 | Platform | Platform | Fullstack | Must | MVP | 8 | 13 |  |  | NB-188, NB-262 | Failed-delivery and quality drilldown available per tenant | Not started
NB-265 | E22 Platform Console — SaaS Operations | Platform | Support tickets with SLA & multi-source raising | Raised by owners, staff and doctors, with system alerts raising their own. | SSA-08 | Platform | Platform | Fullstack | Must | MVP | 8 | 14 |  |  | NB-257, NB-262 | System alerts create tickets automatically; SLA breach is visible and escalates | Done
NB-266 | E22 Platform Console — SaaS Operations | Platform | Support access with consent gate & clinical field blindness | A support engineer never sees clinical fields, using the same overlay the clinic sees. Access is consented, time-boxed and audited. | SSA-04 | Platform | Platform | Security | Must | MVP | 8 | 14 |  |  | NB-257, NB-238 | Clinical fields are absent from the support view; no silent impersonation is possible | Done
NB-267 | E22 Platform Console — SaaS Operations | Platform | Subscriptions, dunning & involuntary churn handling | Tier, add-ons, MRR, currency, renewal date and the active/trialing/overdue/suspended ladder. | SSA-05,CAD-13 | Platform | Platform | Fullstack | Must | MVP | 8 | 15 |  |  | NB-261, NB-269 | An overdue account follows the dunning ladder to suspension with the correct notices | Done
NB-268 | E22 Platform Console — SaaS Operations | Platform | Discount approval queue with caps | Within-cap discounts auto-approve; above-cap requests queue for approval and can be rejected. | SSA-05,SYS-06 | Platform | Platform | Fullstack | Must | MVP | 5 | 15 |  |  | NB-267, NB-056 | Above-cap discount cannot be applied without approval; the cap is configurable | Done
NB-269 | E22 Platform Console — SaaS Operations | Platform | Pricing & packaging console | Plan definition, add-ons and per-tenant feature switches. | CAD-13,SYS-20 | Platform | Platform | Fullstack | Must | MVP | 8 | 12 |  |  | NB-008, NB-257 | A plan change reaches the tenant within the stated propagation budget | Done
NB-270 | E22 Platform Console — SaaS Operations | Platform | Territory & commercial geography console | State and region view with tax code, clinic and user counts, MRR, plan mix, month-on-month movement and aggregator demand. | SSA-01,AGG-04 | Platform | Platform | Fullstack | Should | Phase 2 | 8 | 17 |  |  | NB-262, NB-267 | Territory figures reconcile with billing and the aggregator demand feed | Done
NB-271 | E22 Platform Console — SaaS Operations | Platform | Multi-region deployment & residency enforcement | Independent India and KSA stacks with a shared control plane and no cross-region replication. | NFR-04,SYS-14 | Platform | Platform | DevOps | Must | MVP | 13 | 11 |  |  | NB-002, NB-299 | Region failover never moves data across the residency boundary; KMS keys are region-scoped | Not started
NB-272 | E22 Platform Console — SaaS Operations | Platform | Platform audit console | Cross-tenant, read-only audit search for platform operators. | SSA-11,DPO-01,SYS-13 | Platform | Platform | Fullstack | Must | MVP | 5 | 15 |  |  | NB-238, NB-257 | Every platform action is queryable within five minutes of occurring | Done
NB-273 | E22 Platform Console — SaaS Operations | Platform | Per-tenant usage metering & quota enforcement | Message volume, storage and seats, driving billing and abuse control. | SSA-05,NFR-02 | Platform | Platform | Backend | Should | MVP | 5 | 16 |  |  | NB-261, NB-304 | Metering reconciles with provider invoices within 1% | Done
NB-274 | E22 Platform Console — SaaS Operations | Platform | Multi-branch & multi-clinic groups | Branch-scoped queues, staff, stock and reporting under one tenant. |  | Owner | Clinic | Backend | Should | Phase 2 | 8 | 18 |  |  | NB-261, NB-049 | Branch switch rescopes all data with no cross-branch leakage | Not started
NB-275 | E23 Trial, Sales & Growth | Growth | Self-serve trial creation & conversion funnel | A trial clinic created without sales involvement, tracked through to conversion. | SCS-01,SSA-01 | Platform | Platform | Fullstack | Should | MVP | 8 | 14 |  |  | NB-258, NB-276 | A trial clinic is created and reaches first value without any human involvement | Not started
NB-276 | E23 Trial, Sales & Growth | Growth | Digital DPA gate before any patient data | A plan and a signed digital DPA are required before the tenant can hold patient data. | CEO-17,DPO-01 | Platform,Owner | Platform | Fullstack | Must | MVP | 5 | 14 |  |  | NB-242, NB-261 | Patient data entry is blocked until a plan is selected and the DPA is signed and versioned | Not started
NB-277 | E23 Trial, Sales & Growth | Growth | Low-touch inside sales & lead pipeline | Lead capture and pipeline for a low-touch sales motion. | SCS-02 | Platform | Platform | Fullstack | Should | Phase 2 | 5 | 17 |  |  | NB-275 | Leads flow to a pipeline with stage and owner; no manual spreadsheet is required | Not started
NB-278 | E23 Trial, Sales & Growth | Growth | Onboarding success & activation tracking | Cohort activation tracking that identifies stuck tenants. | SCS-03 | Platform | Platform | Fullstack | Should | Phase 2 | 5 | 18 |  |  | NB-275, NB-069 | A stuck tenant is identified automatically with the blocking step named | Not started
NB-279 | E23 Trial, Sales & Growth | Growth | Paid white-glove setup delivery | A chargeable managed-setup workflow tracked to completion. | SCS-04 | Platform | Platform | Fullstack | Could | Phase 2 | 5 | 19 |  |  | NB-278 | White-glove engagements are tracked with deliverables and a completion gate | Not started
NB-280 | E23 Trial, Sales & Growth | Growth | Trial expiry, conversion & downgrade handling | Trial countdown, conversion and graceful downgrade with historical data preserved. | SCS-01,SYS-20,CAD-13 | Platform,Owner | Platform | Fullstack | Must | MVP | 5 | 16 |  |  | NB-275, NB-267 | Trial expiry never destroys data; downgrade leaves history readable | Not started
NB-281 | E23 Trial, Sales & Growth | Growth | Plan win/loss & pricing signal reporting | Which plans win and lose, feeding pricing decisions. | SCS-04,SCS-02 | Platform | Platform | Fullstack | Could | Phase 2 | 3 | 20 |  |  | NB-277 | Win/loss reasons are captured as structured data, not free text alone | Not started
NB-282 | E24 Cybersecurity | Security | Threat model & security architecture review | STRIDE across auth, tenancy, messaging, billing, aggregator and clinical data flows. |  | All | Shared | Security | Must | MVP | 8 | 2 |  |  | NB-001 | Threat model reviewed; mitigations tracked as backlog items | Not started
NB-283 | E24 Cybersecurity | Security | Region-scoped encryption at rest & KMS key management | Per-tenant keys held in a region-scoped KMS with no cross-region replication of keys or data. | NFR-04 | All | Shared | Security | Must | MVP | 8 | 5 |  |  | NB-009, NB-299 | Key rotation exercised in staging without downtime; keys never leave their region | Not started
NB-284 | E24 Cybersecurity | Security | Encryption in transit & TLS hardening | TLS 1.3, HSTS preload, no weak ciphers, automated certificates. |  | All | Shared | Security | Must | MVP | 3 | 5 |  |  | NB-299 | SSL Labs A+ on all public endpoints | Not started
NB-285 | E24 Cybersecurity | Security | PHI field-level encryption & tokenisation | National identifiers and sensitive fields encrypted at column level. |  | All | Shared | Security | Must | MVP | 5 | 8 |  |  | NB-283, NB-255 | A database dump exposes no plaintext national identifier | Not started
NB-286 | E24 Cybersecurity | Security | Input validation & injection defence | Parameterised queries, schema validation on every endpoint, output encoding. |  | All | Shared | Security | Must | MVP | 5 | 6 |  |  | NB-005 | SAST and DAST report zero high-severity injection findings | Not started
NB-287 | E24 Cybersecurity | Security | OWASP Top 10 & API Top 10 remediation pass | Systematic review including IDOR/BOLA on every patient-scoped and family-scoped route. |  | All | Shared | Security | Must | MVP | 8 | 16 |  |  | NB-050, NB-286 | No high or critical findings open at release | Not started
NB-288 | E24 Cybersecurity | Security | Rate limiting, bot & abuse protection | Per IP, tenant, user and phone number. The unified aggregator number is a public entry point and needs its own limits. | AGG-01,NFR-02 | All | Shared | Security | Must | MVP | 8 | 10 |  |  | NB-006 | Load test confirms limits; the shared aggregator number resists enumeration and flooding | Not started
NB-289 | E24 Cybersecurity | Security | Messaging channel abuse & impersonation controls | Preventing a hijacked or spoofed number from reaching patient data through the chat surface. | PAT-01,CGV-06 | Patient | Patient | Security | Must | MVP | 8 | 15 |  |  | NB-201, NB-288 | A number change requires re-verification before any patient data is released | Not started
NB-290 | E24 Cybersecurity | Security | Secrets scanning & dependency vulnerability management | SCA in CI, SBOM per release, patch SLA by severity. |  | All | Shared | Security | Must | MVP | 5 | 6 |  |  | NB-298 | Build fails on a critical CVE; SBOM published per release | Not started
NB-291 | E24 Cybersecurity | Security | Security headers & frontend hardening | CSP in enforce mode, framing protections, no inline script, subresource integrity. |  | All | Shared | Security | Must | MVP | 3 | 9 |  |  | NB-017 | CSP enforced with zero violations in production | Not started
NB-292 | E24 Cybersecurity | Security | File upload security pipeline | Type verification, size limits, AV scan, sandboxed rendering and no direct object URLs. | SYS-18 | All | Shared | Security | Must | MVP | 5 | 12 |  |  | NB-009 | EICAR test file rejected; only signed short-lived URLs are issued | Not started
NB-293 | E24 Cybersecurity | Security | Security logging, SIEM & alerting | Auth failures, privilege changes, break-glass, support access and mass export all alerted. | SSA-05,SYS-13 | Platform | Shared | Security | Must | MVP | 8 | 16 |  |  | NB-238, NB-304 | Detection rules fire in a simulated attack drill | Not started
NB-294 | E24 Cybersecurity | Security | Annual CERT-In-empanelled VAPT — India | India requires an annual VAPT by a CERT-In empanelled assessor, plus an annual drill with tenants. | NFR-09 | All | Shared | Security | Must | MVP | 13 | 20 |  |  | NB-287, NB-050 | CERT-In empanelled assessor engaged; all critical and high findings closed and retested | Not started
NB-295 | E24 Cybersecurity | Security | KSA penetration test & remediation | Independent external test covering the KSA stack before go-live in that region. | NFR-09 | All | Shared | Security | Must | MVP | 8 | 20 |  |  | NB-287, NB-271 | All critical and high findings closed and retested; report archived | Not started
NB-296 | E24 Cybersecurity | Security | Business continuity & ransomware resilience | Immutable backups, isolated recovery environment and a restore drill. |  | Platform | Shared | Security | Must | MVP | 8 | 19 |  |  | NB-306 | Full restore to a clean environment demonstrated within RTO | Not started
NB-297 | E25 DevOps & Infrastructure | DevOps | Repository, branching & code-review policy | Trunk-based with short-lived branches, mandatory review and signed commits. |  | All | Shared | DevOps | Must | MVP | 3 | 1 |  |  |  | Branch protection enforced; no direct pushes to main | Not started
NB-298 | E25 DevOps & Infrastructure | DevOps | CI pipeline — build, lint, unit test, SAST | Every pull request gated with feedback in under ten minutes. |  | All | Shared | DevOps | Must | MVP | 5 | 1 |  |  | NB-297 | Pipeline green required to merge; median runtime under ten minutes | Not started
NB-299 | E25 DevOps & Infrastructure | DevOps | Infrastructure as code | Every environment and both regions defined in code with no console changes. | NFR-04 | All | Shared | DevOps | Must | MVP | 8 | 2 |  |  | NB-001 | Environment reproducible from scratch in a clean account | Not started
NB-300 | E25 DevOps & Infrastructure | DevOps | Containerisation & orchestration | Container images with resource limits on a managed orchestration platform. |  | All | Shared | DevOps | Must | MVP | 8 | 3 |  |  | NB-299 | Rolling deploy with zero dropped requests | Not started
NB-301 | E25 DevOps & Infrastructure | DevOps | Environment strategy — dev, test, staging, production | Isolated data; staging mirrors production topology; no PHI outside production. |  | All | Shared | DevOps | Must | MVP | 5 | 3 |  |  | NB-299 | Staging seeded with synthetic data only, verified by scan | Not started
NB-302 | E25 DevOps & Infrastructure | DevOps | CD pipeline with progressive delivery | Automated deploy, canary or blue-green, one-click rollback. |  | All | Shared | DevOps | Must | MVP | 8 | 5 |  |  | NB-300, NB-298 | Rollback completes in under five minutes in a drill | Not started
NB-303 | E25 DevOps & Infrastructure | DevOps | Zero-downtime database migration automation | Expand-contract migrations through the pipeline with a rollback plan. |  | All | Shared | DevOps | Must | MVP | 5 | 6 |  |  | NB-004, NB-302 | Migration applied to a production-sized dataset with no downtime | Not started
NB-304 | E25 DevOps & Infrastructure | DevOps | Observability — metrics, logs, traces with PHI redaction | Structured logs with PHI redaction, distributed tracing and RED/USE dashboards. |  | All | Shared | DevOps | Must | MVP | 8 | 7 |  |  | NB-300 | Automated scanner confirms no PHI in logs; traces span the full request | Not started
NB-305 | E25 DevOps & Infrastructure | DevOps | Alerting, on-call & runbooks | SLO-based alerts with an escalation policy and a runbook per alert. |  | All | Shared | DevOps | Must | MVP | 5 | 9 |  |  | NB-304 | Every alert links to a runbook; no unactionable alerts | Not started
NB-306 | E25 DevOps & Infrastructure | DevOps | Backup, retention & restore automation | Point-in-time recovery with encrypted copies held inside the residency boundary. | NFR-04 | All | Shared | DevOps | Must | MVP | 5 | 8 |  |  | NB-299, NB-283 | Automated monthly restore test passes; no backup crosses a region boundary | Not started
NB-307 | E25 DevOps & Infrastructure | DevOps | Disaster recovery — RTO/RPO definition & drill | Target RTO four hours, RPO fifteen minutes, documented and exercised per region. |  | All | Shared | DevOps | Must | MVP | 8 | 18 |  |  | NB-306, NB-271 | DR drill meets the stated RTO and RPO with evidence, in both regions | Not started
NB-308 | E25 DevOps & Infrastructure | DevOps | Background job platform & scheduled workers | Recall, expiry, retention, dunning, reminder and aggregation jobs — idempotent and observable. | PAT-20,PKG-13,CMP-05 | All | Shared | DevOps | Must | MVP | 8 | 8 |  |  | NB-300, NB-007 | Every scheduled job is idempotent and re-runnable without side effects | Not started
NB-309 | E25 DevOps & Infrastructure | DevOps | Cost monitoring & capacity planning | Per-tenant cost attribution, budget alerts and autoscaling policy. |  | Platform | Shared | DevOps | Should | MVP | 3 | 18 |  |  | NB-304 | Cost per tenant reported monthly with alerts at 80% of budget | Not started
NB-310 | E25 DevOps & Infrastructure | DevOps | Release management & change control | Change advisory for clinically-affecting releases, release notes and freeze windows. |  | All | Shared | DevOps | Must | MVP | 3 | 20 |  |  | NB-302 | Every production change traceable to an approved ticket | Not started
NB-311 | E25 DevOps & Infrastructure | DevOps | Provisioning automation hooks | The infrastructure side of the provisioning job engine — schema migration, seeding and WhatsApp provisioning. | SSA-01 | Platform | Platform | DevOps | Must | MVP | 8 | 10 |  |  | NB-299, NB-308 | Each provisioning step is independently retryable and idempotent | Not started
NB-312 | E26 Quality Assurance | QA | Test strategy & quality gates | Pyramid targets, coverage thresholds, definition of done and risk-based clinical focus. |  | All | Shared | QA | Must | MVP | 5 | 2 |  |  | NB-001 | Strategy signed off; gates enforced in CI | Not started
NB-313 | E26 Quality Assurance | QA | Unit & integration test framework | Shared fixtures, tenant-aware factories and per-test database isolation. |  | All | Shared | QA | Must | MVP | 5 | 4 |  |  | NB-312, NB-298 | 70% line coverage on domain logic; suite under eight minutes | Done
NB-314 | E26 Quality Assurance | QA | API contract testing | Consumer-driven contracts between the BFF, services and clients. |  | All | Shared | QA | Must | MVP | 5 | 7 |  |  | NB-005, NB-313 | A breaking API change fails CI before staging | Not started
NB-315 | E26 Quality Assurance | QA | End-to-end automation — clinical & billing journeys | Register, queue, vitals, consult, prescribe, checkout, invoice — per role. |  | All | Shared | QA | Must | MVP | 8 | 13 |  |  | NB-301, NB-162, NB-102 | E2E suite green nightly on staging in all three interface languages | Not started
NB-316 | E26 Quality Assurance | QA | Patient WhatsApp conversation test harness | Automated conversation-flow testing against a provider sandbox, covering tap budgets and session-window expiry. | PAT-03,NFR-02 | Patient | Patient | QA | Must | MVP | 8 | 17 |  |  | NB-202, NB-301 | Tap budgets asserted automatically; session-window expiry behaviour verified without a live provider | Not started
NB-317 | E26 Quality Assurance | QA | RBAC negative-test suite | Automated assertion that every role is denied every permission it does not hold, for both clinic and SaaS operator roles. | SSA-02 | All | Shared | QA | Must | MVP | 8 | 12 |  |  | NB-050, NB-257, NB-313 | Full role x endpoint matrix executed each build for all twelve roles | Not started
NB-318 | E26 Quality Assurance | QA | Cross-browser & device matrix testing | Chrome, Safari and Edge; Android tablets and low-end phones common in clinics. |  | All | Shared | QA | Must | MVP | 5 | 18 |  |  | NB-315 | Matrix documented; no P1 defect on supported devices | Not started
NB-319 | E26 Quality Assurance | QA | RTL & localisation test suite | Visual regression in Arabic and Hindi including Hijri dates, currency, anatomy non-mirroring and chart time axes. | DENT-01,DERM-04 | All | Shared | QA | Must | MVP | 8 | 16 |  |  | NB-031, NB-315 | Screenshot diffs reviewed per release; anatomy and time axes verified unmirrored | Not started
NB-320 | E26 Quality Assurance | QA | Accessibility audit — WCAG 2.2 AA | Automated scans plus manual keyboard and screen-reader passes, including chart table views. |  | All | Shared | QA | Must | MVP | 8 | 18 |  |  | NB-013, NB-027, NB-315 | Zero critical violations; keyboard-only journey completes; charts readable via table view | Not started
NB-321 | E26 Quality Assurance | QA | Clinical safety test cases & hazard log | Allergy, dose, wrong-patient, wrong-family-member and lost-note hazards with evidenced mitigations. | DERM-05,PED-05,GYN-03,CGV-04 | Doctor,Nurse | Shared | QA | Must | MVP | 8 | 19 |  |  | NB-108, NB-112, NB-145 | Hazard log reviewed and signed by the clinical safety officer | Not started
NB-322 | E26 Quality Assurance | QA | Tax & invoice correctness test pack | Independent verification of GST and ZATCA output against worked examples in both regions. | SYS-09 | Owner | Clinic | QA | Must | MVP | 8 | 17 |  |  | NB-163, NB-164 | Every worked example reproduces to the paisa/halala; reviewed by a tax specialist | Not started
NB-323 | E26 Quality Assurance | QA | UAT with pilot clinics in India & KSA | Structured scripts per role, defect triage and sign-off. |  | All | Shared | QA | Must | MVP | 8 | 22 |  |  | NB-315, NB-346 | Both pilot clinics sign off with no open P1 or P2 | Not started
NB-324 | E27 Performance, Reliability & Offline | Performance | Performance budgets & frontend optimisation | The owner dashboard opens in under two seconds on mobile; the queue screen is interactive in under two seconds on a mid-range Android over 4G. | OWN-01,NFR-02 | All | Shared | Frontend | Must | MVP | 8 | 17 |  |  | NB-017, NB-304 | Lighthouse and real-user monitoring meet budget on the pilot device | Not started
NB-325 | E27 Performance, Reliability & Offline | Performance | Database indexing & query optimisation | Tenant-scoped indexes, N+1 elimination and slow-query alerting. |  | All | Shared | Backend | Must | MVP | 5 | 17 |  |  | NB-003, NB-304 | No query over 200ms at p95 under load | Not started
NB-326 | E27 Performance, Reliability & Offline | Performance | Caching strategy | Reference data, entitlements and catalogue cached with correct invalidation. | SYS-20 | All | Shared | Backend | Should | MVP | 5 | 18 |  |  | NB-010, NB-008 | Stale-entitlement window under 60s; cache hit rate above 80% | Not started
NB-327 | E27 Performance, Reliability & Offline | Performance | Load & stress testing | Peak morning-rush profile across clinics plus unbounded patient-side messaging concurrency. | NFR-02,NFR-12 | All | Shared | QA | Must | MVP | 8 | 19 |  |  | NB-301, NB-304 | System meets SLOs at twice expected peak on both the clinic and patient sides | Not started
NB-328 | E27 Performance, Reliability & Offline | Performance | Offline queue, replay & sync banner | Queued writes replay in order; no destructive action is offered while queued. A sync queue is a clinic working offline, not lost data. | NFR-12,SYS-22 | Reception,Nurse | Clinic | Frontend | Must | MVP | 8 | 18 |  |  | NB-020, NB-007 | Queued writes replay in order after reconnect with no duplicates and no lost writes | Not started
NB-329 | E27 Performance, Reliability & Offline | Performance | SLO definition & error budget policy | Availability and latency SLOs per critical journey. |  | All | Shared | DevOps | Must | MVP | 3 | 18 |  |  | NB-304 | SLOs published; error budget policy agreed | Not started
NB-330 | E27 Performance, Reliability & Offline | Performance | Graceful degradation for third-party outages | A WhatsApp, gateway, ZATCA or lab outage must never block clinical or billing work. | SYS-01,NFR-12 | All | Shared | Backend | Must | MVP | 8 | 19 |  |  | NB-193, NB-168 | Chaos test: each provider down in turn, core journeys still complete | Not started
NB-331 | E27 Performance, Reliability & Offline | Performance | Messaging backpressure & provider rate-limit handling | Respecting provider capacity with backpressure rather than dropping messages. | NFR-02 | Platform | Patient | Backend | Must | MVP | 5 | 19 |  |  | NB-200 | Provider rate limit reached: messages queue and drain, none are lost | Not started
NB-332 | E27 Performance, Reliability & Offline | Performance | Read-model lag monitoring | Reporting lag is visible and bounded so the owner never acts on stale money figures unknowingly. | OWN-01 | Owner | Clinic | Backend | Should | MVP | 3 | 19 |  |  | NB-228, NB-304 | Read-model staleness is displayed as an as-of time on every money surface | Not started
NB-333 | E28 Mobile, Tablet & Display Surfaces | Mobile | Mobile shell — bottom nav, FAB, safe areas | Maximum five destinations plus More; 64px nav plus safe area. |  | All | Shared | Frontend | Must | MVP | 5 | 8 |  |  | NB-017 | Matches the wireframe at 360-430px widths | Not started
NB-334 | E28 Mobile, Tablet & Display Surfaces | Mobile | Tablet rail & split-panel layouts | 88px rail and split panel at 1024x1366 — the clinic's primary device. |  | All | Shared | Frontend | Must | MVP | 5 | 9 |  |  | NB-017 | Verified in both orientations | Not started
NB-335 | E28 Mobile, Tablet & Display Surfaces | Mobile | Table-to-card transformation below 768px | Grouped mobile list rows with progressive detail in a bottom sheet. |  | All | Shared | Frontend | Must | MVP | 5 | 9 |  |  | NB-014 | No table renders under 768px anywhere in the product | Not started
NB-336 | E28 Mobile, Tablet & Display Surfaces | Mobile | Bottom sheets replacing dropdowns and popovers on mobile | Every dropdown, select and popover under 768px becomes a sheet. |  | All | Shared | Frontend | Must | MVP | 3 | 10 |  |  | NB-014 | Automated check: no popover positioned off-screen on mobile | Not started
NB-337 | E28 Mobile, Tablet & Display Surfaces | Mobile | Waiting-room token display surface | A full-screen browser display that is its own scale, not a breakpoint — now-serving at 56/62px and next-three raised to 32px for three-metre legibility. | RCP-14 | Reception | Clinic | Frontend | Must | MVP | 8 | 12 |  |  | NB-094, NB-096 | Legible at three metres; shows no patient name by default | Not started
NB-338 | E28 Mobile, Tablet & Display Surfaces | Mobile | Display liveness — paired, stale & connection lost | Re-checked every three seconds. The display must never show a silently frozen token. | RCP-14 | Reception | Clinic | Frontend | Must | MVP | 5 | 13 |  |  | NB-337 | No update within three seconds turns the pill stale; a dropped connection says so explicitly | Not started
NB-339 | E28 Mobile, Tablet & Display Surfaces | Mobile | Display pairing & device management | Pairing a screen to a clinic and managing paired devices. | RCP-14,CAD-01 | Reception,Owner | Clinic | Fullstack | Must | MVP | 5 | 13 |  |  | NB-337 | An unpaired screen is reported in the setup checklist; pairing is revocable | Not started
NB-340 | E28 Mobile, Tablet & Display Surfaces | Mobile | Touch target & ergonomics audit | 44x44 minimum everywhere on touch, including icon-only controls. |  | All | Shared | QA | Must | MVP | 3 | 18 |  |  | NB-333, NB-334 | Automated measurement across every screen passes | Not started
NB-341 | E28 Mobile, Tablet & Display Surfaces | Mobile | PWA — installability, offline shell & push | Installable on clinic tablets with an offline shell and push notifications. | NFR-12 | All | Shared | Frontend | Should | Phase 2 | 8 | 20 |  |  | NB-333, NB-328 | Installs on Android and iOS; the offline shell loads without network | Not started
NB-342 | E29 Launch, Migration & Handover | Launch | Data migration toolkit from legacy systems | Patient, appointment and invoice import with validation and dry-run. | SYS-23 | Owner | Shared | Backend | Should | MVP | 8 | 19 |  |  | NB-071, NB-162, NB-068 | A dry-run report precedes every write; rollback available | Not started
NB-343 | E29 Launch, Migration & Handover | Launch | Requirement traceability & coverage sign-off | Every requirement ID in the wireframe register is mapped to a delivered, tested task before go-live. |  | All | Shared | Delivery | Must | MVP | 5 | 22 |  |  | NB-315 | Coverage report shows zero uncovered MVP requirement IDs | Not started
NB-344 | E29 Launch, Migration & Handover | Launch | Pilot rollout plan & rollback criteria | Two pilot clinics per region with defined success metrics and abort triggers. |  | All | Shared | Delivery | Must | MVP | 5 | 22 |  |  | NB-323 | Plan approved; rollback rehearsed | Not started
NB-345 | E29 Launch, Migration & Handover | Launch | User documentation & in-app guidance per role | Role-specific help and first-run tours in all three interface languages. | NFR-18 | All | Shared | Delivery | Must | MVP | 5 | 20 |  |  | NB-030, NB-315 | Docs published in EN/AR/HI; tour completion tracked | Not started
NB-346 | E29 Launch, Migration & Handover | Launch | Staff training & train-the-trainer | Reception, nurse, doctor, owner and platform-operator tracks with a competency check. |  | All | Shared | Delivery | Must | MVP | 8 | 21 |  |  | NB-345 | All pilot staff certified before go-live | Not started
NB-347 | E29 Launch, Migration & Handover | Launch | Support model, SLA & escalation | Tiered support, ticketing and a clinical-impact escalation path, wired to the platform ticket console. | SSA-08 | Platform | Platform | Delivery | Must | MVP | 3 | 22 |  |  | NB-305, NB-265 | SLA published; escalation tested end to end | Not started
NB-348 | E29 Launch, Migration & Handover | Launch | Staff security awareness & data handling training | Onboarding and annual refresher with tracked completion, plus the annual tenant drill. | NFR-09 | All | Shared | Compliance | Should | MVP | 3 | 22 |  |  | NB-248 | 100% completion before go-live; annual drill scheduled | Not started
NB-349 | E29 Launch, Migration & Handover | Launch | Go-live readiness review & sign-off | Security, compliance, clinical safety, tax, performance and support gates all green. |  | All | Shared | Delivery | Must | MVP | 5 | 23 |  |  | NB-294, NB-295, NB-323, NB-307, NB-327, NB-322, NB-343 | Signed readiness checklist from every gate owner, per region | Not started
NB-350 | E05 Identity, Auth & Session | Auth | Owner account — Brand/Clinic hierarchy & workspace login | Owner is a new top-level account (not a row in any clinic's staff table) that owns Brand(s), each containing Clinic(s). PIN login issues a short-lived pendingToken scoped only to listing/selecting a workspace; selecting a clinic mints a normal staff-shaped access/refresh token pair via a lazily-created shadow staff row (staff.owner_id), reusing every existing clinic endpoint's RBAC checks unchanged. Clinic (tenants) remains the RLS boundary; brand-wide RLS support (app.accessible_tenant_ids) shipped at the DB layer but has no consuming dashboard endpoint yet. |  | Owner | Shared | Security | Must | MVP |  |  |  |  | NB-040, NB-043, NB-049 | Selecting a clinic the owner doesn't own returns 404, not 403; workspace listing never includes another owner's brands or clinics; the minted clinic token works unchanged against every existing staff-facing endpoint; selecting the same clinic twice reuses one shadow staff row, not a duplicate | Done
NB-351 | E05 Identity, Auth & Session | Auth | Super Admin — dedicated operator login (master schema) | Platform operators (super_admin, implementation, support_engineer, billing, sre, commercial, compliance_dpo) are a separate identity domain from clinic staff/owners, not a reserved tenant reusing staff login. master.operators/sessions/login_attempts live in a dedicated master Postgres schema, outside the tenant-scoped public schema and its RLS. PlatformAuthService mirrors the staff/owner login path's proven lockout (no self-renewal on repeated still-locked hits) and session-ownership (revoke only ever targets the caller's own session) fixes from day one, plus refresh-token rotation with family-based reuse detection and TOTP MFA. Matching /platform/login frontend page, same design tokens as /login, no clinic-code field since operators aren't tenant-scoped. |  | Super Admin | Shared | Security | Must | MVP |  |  |  |  | NB-002, NB-040 | POST /v1/platform/auth/login + /mfa/verify + /refresh + /logout + /sessions all work against master.operators, never public.staff; a still-locked login hit does not extend the lockout window; DELETE /v1/platform/auth/sessions/{id} 404s for a session owned by another operator; a reused refresh token revokes its whole family, including the token just rotated to; /platform/login renders and authenticates against a live backend | Done
TOTAL
NB-352 | E22 Platform Console — SaaS Operations | Platform | Tenant Provisioning console page | Frontend for the provisioning job queue (NB-258/259/260/261) — create a job, approve enterprise-gated jobs, advance and inspect each of the six steps with its status and error detail. | SSA-01 | Platform | Platform | Frontend | Must | MVP | 5 |  |  |  | NB-258, NB-259, NB-260, NB-261 | Every step is inspectable with its own status and error detail; enterprise-path jobs cannot advance before approval | Done
NB-353 | E22 Platform Console — SaaS Operations | Platform | Provisioning creates the owner's real login | verify_invite_owner now creates a real, login-capable staff row for the owner (reusing StaffService.invite/acceptInvite) instead of logging a mock invite line. Captures ownerMobile at provisioning time so the existing WhatsApp-OTP PIN reset (AuthService.requestPinReset) works for this owner from day one. Sends the invite link by real email via Gmail SMTP (EmailSender seam: SmtpEmailSender when SMTP_HOST is configured, LoggingEmailSender otherwise — every local/test run today). The raw invite token is still also returned once on the advance() response as a manual-relay fallback if the email never lands. | SSA-01 | Owner | Platform | Fullstack | Must | MVP | 5 |  |  |  | NB-258 | verify_invite_owner creates a staff row for the owner (status invited) with a hashed invite token; advance() returns the raw invite token exactly once, on the response immediately after that step runs; a fatal failure on a later step rolls back and deletes that staff row; retrying advance() after the owner is already invited does not create a duplicate row. When SMTP_HOST is configured, the owner also receives a real email containing the invite link. | Done
NB-355 | E10 Queue, Scheduling & Availability | Queue | Departments + inter-department transfer | A first-class per-tenant Department entity (e.g. Dental, Dermatology) that a visit is routed to at check-in, replacing the single hardcoded pipeline with a per-department requiresVitals toggle (skip the vitals step entirely). An owner-designed transfer graph (department_transfers) lets a doctor mid-consultation send a patient into another department's queue instead of billing this leg — closes the current queue_entries row (transferred_out) and opens a linked one (parent_queue_entry_id) in the target department, reusing the existing checkout pipeline unchanged per leg. Every already-provisioned tenant is backfilled with a default department so nothing existing breaks the moment this ships. |  | Owner,Reception,Nurse,Doctor | Clinic | Fullstack | Must | MVP | [5 empty] | An existing tenant's check-in/vitals/consult/checkout behavior is unchanged after the migration; a department with requiresVitals=false skips straight from waiting to in_consult; a transfer is only permitted along an owner-configured edge and only from in_consult; each leg of a transferred visit checks out with its own invoice. | Done
NB-356 | E10 Queue, Scheduling & Availability | Queue | Configurable multi-step visit flow per department, with interim billing | Generalizes NB-354's single requires_vitals boolean into a fully reorderable sequence of visit stages per department (visit_flow_steps: billing, vitals, consultation, procedures — check-in/waiting and checkout_pending/completed stay fixed first/last anchors), so an owner can design e.g. Reception -> Billing (consultation fee) -> Vitals -> Consultation -> Checkout for a general clinic, or Reception -> Consultation -> Procedures -> Billing -> Checkout for a dental clinic. Staff are assigned to a department for staffing purposes too (Nursing, Reception, Billing), reusing the same departments table. An interim billing stop is a real, separate payment (e.g. a consultation fee charged before the doctor is seen) — CheckoutService.checkout() now creates the invoice at the FIRST billing checkpoint a visit reaches and appends to the SAME invoice at any later one (including the terminal checkout), so a visit can close out with zero further payment due if nothing else was charged. |  | Owner,Reception,Nurse,Doctor,Billing | Clinic | Fullstack | Must | MVP |  |  |  |  | NB-355 | A department's flow must include exactly one consultation step; an unconfigured department falls back to today's vitals+consultation default; checkout() at an interim billing_pending stop does not mark the visit completed, only the terminal checkout_pending stop does; a second billing checkpoint appends to (not replaces) the existing invoice and its totals are recomputed from every line item on it; the terminal checkout succeeds with zero new line items when nothing further was charged. | Done
NB-357 | E10 Queue, Scheduling & Availability | Queue | Platform-authored workflow templates replace owner-designed visit flow | Phase 1 of the Arogya Fabric restructuring: replaces NB-356's freely-reorderable owner flow editor (visit_flow_steps) with a platform-authored template library (workflow_definitions: clinic_walkin, clinic_walkin_with_billing, dental_procedure) plus a small set of template-defined toggles (currently vitals_enabled). An owner now picks a published template per department and flips its toggles instead of reordering stages directly. department_workflow_selection replaces visit_flow_steps as the per-department row; DepartmentService.resolveStatusSequence (the single source of truth QueueService and CheckoutService both call) is re-pointed to the new tables with its external behavior unchanged. Every already-configured department is backfilled onto the closest matching platform template (or a one-off tenant-scoped snapshot template if nothing matches) so no tenant's live behavior changes. |  | Owner,Reception,Nurse,Doctor,Billing | Clinic | Fullstack | Must | MVP |  |  |  |  | NB-356 | GET /v1/departments/{id}/flow keeps returning the resolved, ordered step list unchanged for consult/checkout/nursing pages; an unconfigured department still falls back to vitals+consultation; POST /v1/departments/{id}/workflow accepts only a published templateCode plus toggles the chosen template defines, rejecting an unknown template code or a toggle the template does not define; the general-clinic and dental-clinic examples from NB-355/356 resolve identically when configured via clinic_walkin_with_billing and dental_procedure; the V40 migration backfill preserves every existing department's exact resolved sequence. | Done
NB-358 | E01 Foundation & Architecture | Architecture | Org hierarchy + commercial axis: additive schema (Arogya Fabric Phase 2) | Phase 2 of the Arogya Fabric restructuring: additive-only schema from the architecture doc's org hierarchy and commercial axis (S6.3), confirmed against the current model (owners=L1 Tenant, brands=L2 Brand, tenants=L3 Facility, departments=L4 Department -- no isolation-grain change). Adds tenants.facility_type (clinic/single_specialty/multi_specialty) and tenants.billing_mode (defaults to per_department, matching NB-356's actual live checkout behaviour rather than the doc's stated consolidated default); departments.kind and specialty_code; new tenant-scoped, RLS-isolated service_points (L5) and invoice_series tables; new legal_entities/tax_registrations tables scoped by owner_id with no RLS of their own, matching the existing owners/brands precedent (V6). No application code reads any of this yet -- schema only, ahead of the feature that will need it. |  | Platform,Owner | Shared | Architecture | Should | Post-MVP |  |  |  |  | NB-357 | Every already-provisioned tenant defaults to facility_type=clinic, billing_mode=per_department, and its default department to kind=clinical after the migration; service_points and invoice_series rows are only visible within the tenant session that created them (RLS), verified by OrgHierarchySchemaTest; legal_entities/tax_registrations/invoice_series form the doc's Legal Entity -> Tax Registration -> Invoice Series chain with a facility able to reference a tax registration via tenants.tax_registration_id. | Done
NB-359 | E01 Foundation & Architecture | Architecture | Cross-facility data visibility: activate the dormant accessible_tenant_ids GUC (Arogya Fabric Phase 3) | Phase 3 of the Arogya Fabric restructuring: adds brands.data_visibility_scope (FACILITY default / BRAND / TENANT, the doc's S6.3 brand-visibility model) and wires TenantContext.set() -- called on every service method before any RLS-protected query -- to compute app.accessible_tenant_ids fresh from the active tenant's brand scope on every call. Every tenant_isolation policy V6 already patched with the OR tenant_id::text = ANY(accessible_tenant_ids) clause picks this up with zero further changes. FACILITY scope (the default, and any tenant with no brand) resolves to no siblings at all, so this is a no-op for every tenant today; no UI or endpoint yet lets an owner change the scope. |  | Platform,Owner | Shared | Architecture | Should | Post-MVP |  |  |  |  | NB-358 | A tenant with no brand, or a brand at the default FACILITY scope, sees exactly the same rows as before this change on every V6-patched table; a brand set to BRAND scope makes every sibling facility under that brand mutually visible on those tables; a brand set to TENANT scope extends that to every facility across every brand of the same owner; an unrelated brand under the same or a different owner never leaks in; a scope change takes effect on the very next request with no session/cache invalidation needed, verified end-to-end by CrossFacilityVisibilityTest. | Done
NB-360 | E10 Queue, Scheduling & Availability | Queue | Encounter identity + fixed stage vocabulary on queue_entries (Arogya Fabric Phase 4) | Phase 4 of the Arogya Fabric restructuring: begins reconciling queue_entries toward the architecture doc's ENCOUNTER/ENCOUNTER_SEGMENT model (S6.5) without a physical table split -- queue_entries is FK-referenced by clinical_notes, invoices, prescriptions and procedure_orders (V19-V29), so splitting it now would be a large, risky rewrite for a doc-fidelity win nothing built so far needs. Instead queue_entries stays one row per department leg (an ENCOUNTER_SEGMENT) and gains: encounter_id (self-referencing, shared by every leg of one visit, defaulted by a BEFORE INSERT trigger so no Java call site can forget it), class (ambulatory/procedure/teleconsult/inpatient, always ambulatory today), current_stage (the doc's fixed S9.1 stage vocabulary, computed from status by a SQL function + trigger so dashboards can key off a stable set of stages regardless of a department's configured step names), and workflow_definition_id (the platform template governing this leg, resolved from department_workflow_selection at insert). All three triggers/functions are the single source of truth -- no Java-side duplicate of the status-to-stage mapping. |  | Owner,Reception,Nurse,Doctor,Billing | Clinic | Fullstack | Should | Post-MVP |  |  |  |  | NB-359 | A fresh check-in gets encounter_id equal to its own id, class=ambulatory, and current_stage=CHECKED_IN; a transfer propagates the original encounter_id onto the new leg and the closed leg's current_stage becomes COMPLETED; every subsequent status PATCH keeps current_stage in sync automatically; workflow_definition_id is null for an unconfigured department and set to the selected template once one is chosen; every existing row is correctly backfilled by the migration. | Done

## Requirement Coverage
Requirement coverage — every identifier found in the wireframe, and the tasks that deliver it
Extracted programmatically from the wireframe source, not transcribed by hand. Uncovered rows turn red — there must be none.
Requirement ID | Area | Description (from the wireframe) | Work Starts In | Tasks Delivering It | Task Count | Covered?
AGG-01 | Aggregator | Nabd's shared number, invisible routing, verified-visit ratings | MVP | NB-221, NB-224, NB-288 | 3
AGG-02 | Aggregator | This may be an emergency. Call | Phase 2 | NB-222 | 1
AGG-03 | Aggregator |  | Phase 2 | NB-223 | 1
AGG-04 | Aggregator | patient demand on the unified number vs actual coverage — the sales signal | Phase 2 | NB-227, NB-270 | 2
AGG-05 | Aggregator | A verified rating comes only from a completed, paid visit on the platform — fake reviews are impossible. Hidden until 10 ratings, showing \ | Phase 2 | NB-225, NB-226 | 2
AYU-02 | Ayurveda | Panchakarma | Phase 2 | NB-140 | 1
AYU-03 | Ayurveda | Herbal formulation (Ayurveda) | Phase 2 | NB-140 | 1
BIL-06 | Billing | Dues list | MVP | NB-171, NB-233 | 2
BIL-07 | Billing | Price transparency & estimates | MVP | NB-126, NB-170 | 2
BIL-11 | Billing | Insurance claim export | MVP | NB-070, NB-175 | 2
CAD-01 | Setup | Guided clinic setup wizard | MVP | NB-060, NB-069, NB-339 | 3
CAD-04 | Setup | CAD-04 · 24 charge heads | MVP | NB-061 | 1
CAD-05 | Setup | Schedule and calendar admin | MVP | NB-036, NB-064, NB-090, NB-091, NB-092 | 5
CAD-06 | Setup | Simple policy settings | MVP | NB-062 | 1
CAD-07 | Setup | WhatsApp number & template health | MVP | NB-069, NB-188, NB-189, NB-190, NB-239 | 5
CAD-08 | Setup | Consent & privacy notice settings | MVP | NB-063, NB-240 | 2
CAD-09 | Setup | Shift timings & attendance (Phase 2) | MVP | NB-065, NB-092 | 2
CAD-10 | Setup | Simple payroll export | MVP | NB-066 | 1
CAD-11 | Setup | Pharmacy mode configuration | MVP | NB-177 | 1
CAD-12 | Setup | font:600 10px/14px | MVP | NB-041, NB-045 | 2
CAD-13 | Setup | SaaS subscription & plan | MVP | NB-008, NB-067, NB-267, NB-269, NB-280 | 5
CEO-14 | Ruling | Emergency interception | Phase 2 | NB-217, NB-222, NB-225, NB-226 | 4
CEO-15 | Ruling | a booking + check-in convenience plan — not a clinical care contract. | Phase 3 | NB-088, NB-219 | 2
CEO-17 | Ruling | Blocked — requires a plan and a signed digital DPA. | MVP | NB-242, NB-276 | 2
CEO-25 | Ruling | capture-only, consent-worded for this purpose only, no monetisation | MVP | NB-185 | 1
CEO-27 | Ruling | warning plus register — no hard block | Phase 2 | NB-182 | 1
CGV-01 | Family | One WhatsApp number, whole family | MVP | NB-080 | 1
CGV-02 | Family | Add family member with consent capture | MVP | NB-081 | 1
CGV-03 | Family | Minor & guardian handling, age-18 handover | MVP | NB-082 | 1
CGV-04 | Family | Proxy booking, check-in & queue updates | MVP | NB-083, NB-321 | 2
CGV-05 | Family | Dual delivery of visit instructions | MVP | NB-084 | 1
CGV-06 | Family | Proxy revocation & scope change | MVP | NB-085, NB-289 | 2
CGV-07 | Family | Family appointment batching | Phase 2 | NB-086 | 1
CGV-09 | Family | Elderly-parent care alerts | Phase 2 | NB-087 | 1
CGV-10 | Family | Family plan / package sharing | Phase 3 | NB-088, NB-219 | 2
CMP-01 | Compliance | Consent & notice templates | MVP | NB-240 | 1
CMP-02 | Compliance | Consent as a hard gate (owner evidence) | MVP | NB-053, NB-196, NB-241 | 3
CMP-03 | Compliance | Patient rights self-service & queue | MVP | NB-078, NB-214, NB-243, NB-244, NB-253 | 5
CMP-04 | Compliance | Child & guardian protection | MVP | NB-082, NB-089, NB-199, NB-252 | 4
CMP-05 | Compliance | Retention auto-rules | MVP | NB-245, NB-308 | 2
CMP-06 | Compliance | Breach-notification runbook | MVP | NB-248 | 1
CMP-07 | Compliance | India messaging compliance (DLT) | MVP | NB-018, NB-191, NB-194 | 3
CMP-11 | Compliance | Licence & credential expiry tracker | MVP | NB-070, NB-175, NB-250 | 3
CMP-12 | Compliance | Compliance health card + grievance setup | Phase 2 | NB-251 | 1
DENT-01 | Dental | chosen once, clinic-wide. Storage always stays keyed by FDI — switching loses no data. | MVP | NB-032, NB-120, NB-122, NB-319 | 4
DENT-02 | Dental | Radiograph library — tooth-linked, reachable from the chart | MVP | NB-123 | 1
DENT-05 | Dental | dashed outline + superscript = stage order in an active plan (form, not a new colour) | MVP | NB-124 | 1
DENT-06 | Dental | subscription-controlled — historical data stays readable when a trial ends | MVP | NB-058, NB-116, NB-121, NB-125 | 4
DENT-07 | Dental | subscription-controlled — historical data stays readable when a trial ends | MVP | NB-058, NB-121, NB-126 | 3
DENT-08 | Dental | everything ever done to this tooth — procedures, radiographs, medicines, materials — one tap from the chart | Phase 3 | NB-127 | 1
DERM-04 | Derm | subscription-controlled | MVP | NB-032, NB-058, NB-121, NB-128, NB-129, NB-319 | 6
DERM-05 | Derm | Allergy hard-warning with mandatory override reason | MVP | NB-107, NB-108, NB-321 | 3
DERM-06 | Derm | Photo follow-up reminders | Phase 2 | NB-130 | 1
DERM-07 | Derm | subscription-controlled | MVP | NB-058, NB-121 | 2
DOC-01 | Doctor | session strip — status before any detail | MVP | NB-102 | 1
DOC-02 | Doctor | Previous medicines & treatment — read before prescribing | MVP | NB-105 | 1
DOC-03 | Doctor | Availability, leave & block management | MVP | NB-091, NB-155, NB-250 | 3
DOC-05 | Doctor | Clinical note templates | MVP | NB-103 | 1
DOC-06 | Doctor | SFDA identifiers and controlled-substance rules — KSA | MVP | NB-010, NB-109, NB-111 | 3
DOC-09 | Doctor | Signed — DOC-09 — the procedure can proceed | MVP | NB-119 | 1
DOC-11 | Doctor | Print & share visit outputs | MVP | NB-117 | 1
DPO-01 | Data prot. | Consent registry & audit | MVP | NB-242, NB-272, NB-276 | 3
DPO-02 | Data prot. | DSR workflow engine | MVP | NB-244, NB-253 | 2
DPO-03 | Data prot. | Breach management ops | MVP | NB-249 | 1
DPO-04 | Data prot. | seven states, every transition audited | MVP | NB-261 | 1
DPO-05 | Data prot. | Retention & deletion engine | MVP | NB-245, NB-246, NB-247 | 3
DPO-09 | Data prot. | Child-data protection controls | MVP | NB-089, NB-199, NB-252 | 3
ENT-01 | ENT | Endoscopy image/video attach | Phase 2 | NB-139 | 1
ENT-02 | ENT | Audiogram entry & attach | Phase 2 | NB-139 | 1
ENT-03 | ENT | Minor-procedure notes + consent | Phase 2 | NB-139 | 1
GP-02 | Gen. prac. | Chronic reviews due | MVP | NB-074, NB-077 | 2
GP-03 | Gen. prac. | Chart system gallery | MVP | NB-022, NB-023, NB-028 | 3
GP-04 | Gen. prac. | Referral letter generation | MVP | NB-118 | 1
GP-05 | Gen. prac. | Generic name printed first (India NMC norm) | MVP | NB-010, NB-110, NB-111 | 3
GP-06 | Gen. prac. | Favourite Rx sets | MVP | NB-105, NB-109, NB-114 | 3
GP-07 | Gen. prac. | Medical / sick-leave certificate | MVP | NB-118 | 1
GYN-01 | Gynae | Pregnancy tracker (LMP → EDD timeline) | Phase 2 | NB-137 | 1
GYN-02 | Gynae | Ultrasound report attach & review | Phase 2 | NB-138 | 1
GYN-03 | Gynae | Pregnancy and lactation warning — works without the Gynaecology profile | MVP | NB-113, NB-321 | 2
HOM-02 | Homeo | Remedy & potency (Homeopathy) | Phase 2 | NB-141 | 1
MKT-04 | Marketing | Influencer & social attribution | MVP | NB-079, NB-230 | 2
NFR-02 | Non-func. |  | MVP | NB-006, NB-024, NB-029, NB-200, NB-273, NB-288, NB-316, NB-324, NB-327, NB-331 | 10
NFR-04 | Non-func. | no cross-region replication, region-scoped KMS keys | MVP | NB-001, NB-002, NB-254, NB-271, NB-283, NB-299, NB-306 | 7
NFR-06 | Non-func. |  | MVP | NB-040, NB-042 | 2
NFR-07 | Non-func. | Regulator/owner export within 72h — NFR-07 · 3-year retention. | MVP | NB-078, NB-244, NB-247, NB-253 | 4
NFR-08 | Non-func. | Consent is checked at query level — NFR-08. | MVP | NB-053, NB-196, NB-241 | 3
NFR-09 | Non-func. | Annual CERT-In-empanelled VAPT (NFR-09) · annual drill with tenants. | MVP | NB-294, NB-295, NB-348 | 3
NFR-12 | Non-func. | A sync queue means a clinic working offline, not lost data. WhatsApp quality under 60% puts sending at risk. | MVP | NB-007, NB-020, NB-096, NB-263, NB-327, NB-328, NB-330, NB-341 | 8
NFR-18 | Non-func. | Fully self-serve, no support help needed — NFR-18. | MVP | NB-060, NB-068, NB-345 | 3
NUR-05 | Nursing | Clinical triage inbox | MVP | NB-144 | 1
ORTH-01 | Ortho | X-ray attach & review flag | MVP | NB-135 | 1
ORTH-02 | Ortho | Fracture/injury note templates | MVP | NB-135 | 1
ORTH-03 | Ortho | Physio session packages | Phase 2 | NB-136 | 1
OWN-01 | Owner | Daily money dashboard | MVP | NB-025, NB-229, NB-324, NB-332 | 4
OWN-02 | Owner | Where patients come from | MVP | NB-079, NB-230 | 2
OWN-03 | Owner | Repeat-patient & recall value | Phase 2 | NB-234 | 1
OWN-04 | Owner | Staff collection & performance | MVP | NB-231 | 1
OWN-05 | Owner | No-show prediction (rule-based) | Phase 2 | NB-234, NB-235 | 2
OWN-07 | Owner | Day close | MVP | NB-172 | 1
OWN-08 | Owner | Package liability | MVP | NB-161, NB-232 | 2
OWN-09 | Owner | Billing leakage alerts | MVP | NB-233 | 1
PAT-01 | Patient | WhatsApp zero-form registration | MVP | NB-071, NB-201, NB-289 | 3
PAT-03 | Patient | Guided booking, tap-budgeted | MVP | NB-080, NB-202, NB-250, NB-316 | 4
PAT-04 | Patient | Layered reminders with confirmation cascade | MVP | NB-203 | 1
PAT-05 | Patient | Live queue & your-turn tracking | MVP | NB-101, NB-204 | 2
PAT-06 | Patient | Cancel with one-tap reason | MVP | NB-205 | 1
PAT-07 | Patient | Waitlist join & auto-fill offers | MVP | NB-099, NB-208 | 2
PAT-08 | Patient | One-tap reschedule | MVP | NB-206 | 1
PAT-09 | Patient | Arrival check-in — QR or in-chat | MVP | NB-207 | 1
PAT-10 | Patient | Payments, deposits & refunds in chat | MVP | NB-169, NB-209 | 2
PAT-11 | Patient | Post-visit follow-up check-ins | MVP | NB-212 | 1
PAT-13 | Patient | Receive prescriptions & reports securely | MVP | NB-076, NB-213 | 2
PAT-14 | Patient | My data & privacy self-service | MVP | NB-078, NB-214, NB-243 | 3
PAT-15 | Patient | Multilingual & voice-note interaction | MVP | NB-030, NB-039, NB-215 | 3
PAT-16 | Patient | Teleconsultation booking & join | Phase 3 | NB-220 | 1
PAT-17 | Patient | Clinic-branded personal messaging | MVP | NB-198 | 1
PAT-19 | Patient | Smart overbooking protection | MVP | NB-098 | 1
PAT-20 | Patient | Treatment-linked recall engine | MVP | NB-116, NB-125, NB-216, NB-308 | 4
PAT-21 | Patient | Buy a package in WhatsApp (with PKG-04) | Phase 2 | NB-210 | 1
PAT-22 | Patient | Package session tracking | MVP | NB-211 | 1
PAT-24 | Patient | Family & chronic-care memberships | Phase 3 | NB-088, NB-219 | 2
PAT-25 | Patient | Referral rewards | Phase 2 | NB-218 | 1
PAT-26 | Patient | Google-review prompt | Phase 2 | NB-217, NB-226 | 2
PED-01 | Paeds | Vaccines due | MVP | NB-131 | 1
PED-02 | Paeds | a single message — reconciled with PED-02's parent reminder, never two. | MVP | NB-133 | 1
PED-03 | Paeds | Chart system gallery | MVP | NB-022, NB-028, NB-132 | 3
PED-04 | Paeds | PED-04 · triggered by a validated growth service, never calculated in the UI | Phase 2 | NB-132 | 1
PED-05 | Paeds | Weight-based dosing from latest recorded weight | MVP | NB-106, NB-112, NB-321 | 3
PED-06 | Paeds | PED-06 · consent stored separately per guardian | MVP | NB-082 | 1
PED-07 | Paeds | PED-07 · friendly avatar only, no clinical data | Phase 2 | NB-134 | 1
PED-08 | Paeds | PED-08 · content loaded from a versioned clinical source | MVP | NB-131 | 1
PHR-01 | Pharmacy | e-Rx dispensing queue | MVP | NB-179 | 1
PHR-03 | Pharmacy | Full inventory, batch & expiry | Phase 2 | NB-181, NB-187 | 2
PHR-04 | Pharmacy | Controlled-drug register | Phase 2 | NB-182 | 1
PHR-05 | Pharmacy | WhatsApp refill reminders | Phase 2 | NB-184 | 1
PHR-06 | Pharmacy | Pharmacy items on the main bill | MVP | NB-180 | 1
PHR-09 | Pharmacy | One-tap dispense & bill | MVP | NB-180 | 1
PHR-10 | Pharmacy | Low-stock & expiry alerts | Phase 2 | NB-183, NB-187 | 2
PHR-11 | Pharmacy | Bought-where adherence capture | MVP | NB-185 | 1
PHR-12 | Pharmacy | Small-shelf item master | MVP | NB-178, NB-186 | 2
PKG-02 | Packages | Blocking Dr. Meera Iyer affects an active package restricted to this doctor — PKG-02. | MVP | NB-155 | 1
PKG-04 | Packages | My package | Phase 2 | NB-210 | 1
PKG-06 | Packages | Payment plans & auto-collection | Phase 2 | NB-156 | 1
PKG-07 | Packages | Payment plans & auto-collection | Phase 2 | NB-156 | 1
PKG-10 | Packages | Session redemption booking | MVP | NB-147, NB-154 | 2
PKG-12 | Packages | Progress view & next-session nudges | MVP | NB-136, NB-153, NB-158, NB-211 | 4
PKG-13 | Packages | Expiry warnings & grace period | MVP | NB-157, NB-308 | 2
PKG-16 | Packages | Transfer & gifting of remaining sessions | Phase 2 | NB-159 | 1
PKG-17 | Packages | Package liability | MVP | NB-161, NB-232 | 2
PKG-18 | Packages | Package sales, redemption & recognition | MVP | NB-161, NB-232 | 2
RCP-04 | Reception | an owner-only aggregate — no per-patient log, and neither the doctor nor reception sees this | MVP | NB-100, NB-236 | 2
RCP-07 | Reception | NPHIES eligibility-check-lite | Phase 2 | NB-176 | 1
RCP-08 | Reception | prepaid link only — desk counter QR collection (RCP-08) is untouched. | MVP | NB-169 | 1
RCP-11 | Reception | Shared WhatsApp inbox with canned replies | MVP | NB-018, NB-144, NB-197 | 3
RCP-12 | Reception | End-of-day desk summary | MVP | NB-173 | 1
RCP-14 | Reception | re-checked every 3 seconds — no update within that window turns the pill stale, a dropped connection says so explicitly rather than freezing silently. | MVP | NB-069, NB-337, NB-338, NB-339 | 4
SCS-01 | Sales | Self-serve trial & conversion funnel | MVP | NB-260, NB-275, NB-280 | 3
SCS-02 | Sales | Low-touch inside sales | Phase 2 | NB-277, NB-281 | 2
SCS-03 | Sales | Onboarding success & activation tracking | Phase 2 | NB-278 | 1
SCS-04 | Sales | Paid white-glove setup delivery | Phase 2 | NB-279, NB-281 | 2
SSA-01 | SaaS ops | Tenant provisioning & regions | MVP | NB-258, NB-259, NB-260, NB-261, NB-262, NB-270, NB-275, NB-311 | 8
SSA-02 | SaaS ops | seven SaaS-side roles — no single super-admin does everything | MVP | NB-017, NB-054, NB-257, NB-317 | 4
SSA-03 | SaaS ops | WABA fleet quality monitoring | MVP | NB-188, NB-189, NB-190, NB-264 | 4
SSA-04 | SaaS ops | A support engineer never sees clinical fields — the same overlay:\ | MVP | NB-266 | 1
SSA-05 | SaaS ops | Security incident ops | MVP | NB-249, NB-267, NB-268, NB-273, NB-293 | 5
SSA-06 | SaaS ops | sync backlog, WhatsApp quality and error rate per clinic | MVP | NB-262, NB-263 | 2
SSA-08 | SaaS ops | raised by owners, staff and doctors — and system alerts raise their own | MVP | NB-265, NB-347 | 2
SSA-11 | SaaS ops | Regulatory watch | MVP | NB-256, NB-272 | 2
SYS-01 | Platform | SMS fallback fired now | MVP | NB-007, NB-040, NB-193, NB-330 | 4
SYS-02 | Platform | effective immediately (under 1 minute) on every surface — a queued reminder was just suppressed. | MVP | NB-196, NB-199 | 2
SYS-03 | Platform | prayer-window reconciliation | MVP | NB-100, NB-195 | 2
SYS-04 | Platform | visit-type durations from the clinic template; prayer breaks from SYS-04 | MVP | NB-036, NB-090 | 2
SYS-06 | Platform | financial/clinical-safety class — explicit confirmation required | MVP | NB-005, NB-056, NB-099, NB-165, NB-268 | 5
SYS-07 | Platform | Reason (shared SYS-07 list) | MVP | NB-011, NB-097, NB-205 | 3
SYS-09 | Platform | SYS-09 · GST invoice for the full package, delivered in-thread. | MVP | NB-163, NB-164, NB-210, NB-322 | 4
SYS-10 | Platform | Full claims via certified middleware — Phase 3 (SYS-10). Not designed here. | MVP | NB-175, NB-176 | 2
SYS-11 | Platform | Photo follow-up reminders | Phase 2 | NB-130 | 1
SYS-13 | Platform | Review logged to the audit trail | MVP | NB-003, NB-048, NB-104, NB-238, NB-239, NB-272, NB-293 | 7
SYS-14 | Platform | installation secrets are separate from tenant integrations — two different roles | MVP | NB-001, NB-002, NB-009, NB-254, NB-271 | 5
SYS-18 | Platform | a file is never sent into open chat | MVP | NB-075, NB-076, NB-117, NB-174, NB-213, NB-292 | 6
SYS-20 | Platform | upgrade/downgrade without data loss, under 5 minutes | MVP | NB-008, NB-067, NB-269, NB-280, NB-326 | 5
SYS-21 | Platform | every step is skippable and resumable | MVP | NB-060, NB-258 | 2
SYS-22 | Platform | A sync queue means a clinic working offline, not lost data. WhatsApp quality under 60% puts sending at risk. | MVP | NB-263, NB-328 | 2
SYS-23 | Platform | self-serve import & export | MVP | NB-027, NB-068, NB-237, NB-342 | 4
SYS-25 | Platform | The clinic never touches Meta Business Manager — SYS-25 is a fully managed service. | MVP | NB-188 | 1
TOTAL

## Epics
Epic rollup — every cell is a formula reading the Backlog tab
Epic | Tasks | Story Points | % of Total | Est. Person-Days | Must | Should | Could | MVP | Phase 2 | Phase 3 | First Sprint | Last Sprint | Done | % Complete
E01 Foundation & Architecture
E02 Design System & UI Kit
E03 Chart & Data-Visualisation System
E04 Localisation, RTL & i18n
E05 Identity, Auth & Session
E06 RBAC & Permissions
E07 Clinic Setup & Administration
E08 Patient Records & Registration
E09 Caregiver, Family & Guardianship
E10 Queue, Scheduling & Availability
E11 Clinical Workspace
E12 Specialty Workspaces
E13 Nursing, Orders & Triage
E14 Treatment Packages
E15 Billing, Tax & Payments
E16 Pharmacy
E17 Messaging Platform & WhatsApp Infrastructure
E18 Patient WhatsApp Surface
E19 Aggregator & Demand
E20 Owner Insights & Reports
E21 Compliance, Consent & Data Protection
E22 Platform Console — SaaS Operations
E23 Trial, Sales & Growth
E24 Cybersecurity
E25 DevOps & Infrastructure
E26 Quality Assurance
E27 Performance, Reliability & Offline
E28 Mobile, Tablet & Display Surfaces
E29 Launch, Migration & Handover
TOTAL

## Sprints
Sprint load against ramped squad capacity
Capacity = squads that sprint x README!B31. Squad counts are blue input cells — change them and every capacity figure moves.
Sprint | Release Band | Squads | Capacity | Tasks | Story Points | Head-room | Utilisation | Est. Person-Days | Must Tasks | Cumulative Points | % of Programme
1 |  | 2
2 |  | 2
3 |  | 2
4 |  | 2
5 |  | 2
6 |  | 2
7 |  | 3
8 |  | 2
9 |  | 3
10 |  | 3
11 |  | 3
12 |  | 4
13 |  | 4
14 |  | 5
15 |  | 5
16 |  | 5
17 |  | 5
18 |  | 5
19 |  | 4
20 |  | 3
21 |  | 2
22 |  | 2
23 |  | 2
TOTAL
Programme shape
Elapsed weeks
Approximate elapsed months
Peak squads in parallel
Peak people (approx, 6 per squad)
Indicative cost (only if a day rate is set on README)

## Tracks
Parallel delivery tracks
This programme cannot be delivered by one team. These are the four workstreams the backlog naturally separates into.
Track | What it covers | Tasks | Story Points | % of Points | Est. Person-Days | First Sprint | Last Sprint
Shared | Foundation, design system, charts, i18n, auth, security, DevOps and QA — everything the other three depend on
Clinic | Reception, doctor, nurse and owner surfaces: queue, clinical, billing, packages, pharmacy, reports
Patient | The WhatsApp patient surface, caregiver and family handling, messaging infrastructure and the aggregator
Platform | The SaaS console: provisioning, operator roles, subscriptions, support, health, territories and growth
TOTAL

## RBAC Matrix
Clinic role & permission matrix — specification for epic E06
Taken from the wireframe permission model. Y granted, N not granted, P plan/subscription dependent, - not applicable.
Rule: a permission-restricted element is ABSENT, never disabled or greyed. Enforcement is server-side; the UI only reflects it. Consent is additionally checked at query level (NFR-08).
Role | Module | View | Create | Edit | Delete / Void | Approve | Refund / Discount | Export | Notes
Owner / Manager | Patients | Y | Y | Y | Y | Y | - | Y
| Queue & Appointments | Y | Y | Y | Y | Y | - | Y
| Clinical Records | Y | N | N | Y | Y | - | Y
| Billing & Payments | Y | Y | Y | Y | Y | Y | Y
| Packages | Y | Y | Y | Y | Y | Y | Y
| Pharmacy | P | P | P | P | P | P | P | Pharmacy availability follows the tenant plan and pharmacy mode (CAD-11), not the role.
| Reports | Y | - | - | - | Y | - | Y
| Staff & Access | Y | Y | Y | Y | Y | - | Y
| Clinic Setup | Y | - | Y | - | - | - | Y
| Compliance & Audit | Y | - | - | Y | Y | - | Y
Doctor | Patients | Y | Y | Y | - | N | - | - | Scope is per staff member: own patients only, or all clinic patients. Enforced in the query (E06).
| Queue & Appointments | Y | - | Y | - | - | - | -
| Clinical Records | Y | Y | Y | Y | N | - | -
| Billing & Payments | Y | - | - | - | - | - | -
| Packages | Y | Y | Y | - | - | - | -
| Pharmacy | P | P | N | - | - | - | - | External mode removes dispensing entirely; hybrid and in-house are paid tiers.
| Reports | Y | - | - | - | N | - | -
| Staff & Access | N | - | - | - | - | - | -
| Clinic Setup | N | - | - | - | - | - | -
| Compliance & Audit | N | - | - | - | - | - | -
Receptionist | Patients | Y | Y | Y | - | N | - | -
| Queue & Appointments | Y | Y | Y | - | - | - | -
| Clinical Records | N | - | - | - | - | - | -
| Billing & Payments | Y | Y | Y | N | Y | N | - | Refund and discount rights are individually revocable — the wireframe shows a 'no refund, no discount' receptionist.
| Packages | Y | Y | N | - | - | - | -
| Pharmacy | P | P | N | - | - | - | -
| Reports | N | - | - | - | - | - | -
| Staff & Access | N | - | - | - | - | - | -
| Clinic Setup | N | - | - | - | - | - | -
| Compliance & Audit | N | - | - | - | - | - | -
Nurse | Patients | Y | N | Y | - | N | - | -
| Queue & Appointments | Y | - | Y | - | - | - | -
| Clinical Records | Y | Y | Y | - | N | - | - | May be narrowed to vitals and vaccines only.
| Billing & Payments | N | - | - | - | - | - | -
| Packages | Y | - | Y | - | - | - | -
| Pharmacy | P | N | N | - | - | - | -
| Reports | N | - | - | - | - | - | -
| Staff & Access | N | - | - | - | - | - | -
| Clinic Setup | N | - | - | - | - | - | -
| Compliance & Audit | N | - | - | - | - | - | -
Custom (Front Desk + Vitals) | Patients | Y | Y | Y | - | N | - | -
| Queue & Appointments | Y | Y | Y | - | - | - | -
| Clinical Records | Y | Y | N | - | N | - | -
| Billing & Payments | Y | Y | Y | N | Y | N | - | The wireframe's example custom role: 'no financial fields'.
| Packages | Y | Y | N | - | - | - | -
| Pharmacy | P | P | N | - | - | - | -
| Reports | N | - | - | - | - | - | -
| Staff & Access | N | - | - | - | - | - | -
| Clinic Setup | N | - | - | - | - | - | -
| Compliance & Audit | N | - | - | - | - | - | -

## SaaS Operator Roles
Platform-side operator roles (SSA-02) — specification for epic E22
Seven roles. No single super-admin does everything. A role without create rights has no create button anywhere — the element is absent, not disabled.
Surface | Super admin | Implementation | Support engineer | Billing | SRE | Commercial (read-only) | Compliance / DPO
Command Centre | Y | Y | Y | Y | Y | Y | Y
Clinics / fleet | Y | Y | Y | Y | — | Y | Y
Tenant detail | Y | Y | Y | — | — | — | Y
Onboarding / provisioning | Y | Y | — | — | — | — | —
Provisioning jobs | Y | Y | — | — | Y | — | —
Billing & revenue | Y | — | — | Y | — | Y | —
Support tickets | Y | Y | Y | — | — | — | —
Pricing & packaging | Y | — | — | Y | — | — | —
Territories | Y | — | — | — | Y | Y | Y
Messaging operations | Y | Y | — | — | Y | — | —
Platform health | Y | — | Y | — | Y | — | —
Aggregator & demand | Y | — | — | — | — | Y | —
Support access | Y | Y | Y | — | — | — | —
Audit & compliance | Y | — | — | — | Y | — | Y
Hard rules from the wireframe
• Only Super admin and Implementation may create a tenant. For every other role no create button exists anywhere (SSA-02).
• A support engineer never sees clinical fields — the same restricted overlay the clinic itself sees (SSA-04).
• Support access into a tenant requires consent, is time-boxed, shows the tenant a banner, and is fully audited.
• Commercial is read-only by construction, not by convention.
• Compliance / DPO reaches audit and residency surfaces but not billing or provisioning.

## Security Controls
Cybersecurity, privacy and compliance control checklist
Each control names the backlog task that delivers it. Use this as the pre-go-live gate.
Domain | Control | Delivered by | Task ID | Priority | Gate | Verified? | Evidence / Link
Identity | Staff sign-in limited to WhatsApp OTP, short PIN or authenticator app — no SSO, no hardware keys (NFR-06) | Staff authentication — WhatsApp OTP | NB-040 | Must | Go-live blocker | No
Identity | Verified email and mobile both required before any patient data is reachable (CAD-12) | Dual-channel staff identity | NB-041 | Must | Go-live blocker | No
Identity | Authenticator MFA enforced for Owner, Platform operators and refund/discount holders | Authenticator-app MFA enforcement | NB-042 | Must | Go-live blocker | No
Identity | Short-lived tokens, rotating refresh, reuse detection, remote session revoke | Session management & device trust | NB-043 | Must | Go-live blocker | No
Identity | Shared-workstation auto-lock without losing draft clinical notes | Idle timeout & clinical screen lock | NB-044 | Must | Go-live blocker | No
Identity | Break-glass access is time-boxed, reason-captured and loudly alerted | Break-glass emergency access | NB-048 | Should | Post-launch acceptable | No
Access control | Deny-by-default server-side authorisation on every endpoint | Server-side policy enforcement point | NB-050 | Must | Go-live blocker | No
Access control | Row-level patient scoping enforced in the query, not by post-filtering | Row-level scoping | NB-051 | Must | Go-live blocker | No
Access control | Field-level restrictions applied in the API response, not merely hidden in the UI | Field-level restrictions | NB-052 | Must | Go-live blocker | No
Access control | Consent evaluated at query level — the UI is not the enforcement point (NFR-08) | Consent checked at query level | NB-053 | Must | Go-live blocker | No
Access control | Maker-checker on refunds, large discounts and clinical amendments | Approval workflows & maker-checker | NB-056 | Must | Go-live blocker | No
Access control | Restricted elements are absent from the UI, never disabled | UI permission rendering contract | NB-054 | Must | Go-live blocker | No
Access control | Seven segregated SaaS operator roles; no single super-admin does everything (SSA-02) | Seven SaaS operator roles | NB-257 | Must | Go-live blocker | No
Access control | Support engineers are blind to clinical fields (SSA-04) | Support access with consent gate | NB-266 | Must | Go-live blocker | No
Tenancy | Tenant isolation verified by test; no cross-tenant read path | Multi-tenancy isolation model | NB-002 | Must | Go-live blocker | No
Tenancy | Region locked irreversibly at provisioning; no cross-region replication (SYS-14 / NFR-04) | Multi-region deployment & residency | NB-271 | Must | Go-live blocker | No
Tenancy | Installation secrets separated from tenant integration secrets (SYS-14) | Config & secrets management with role | NB-009 | Must | Go-live blocker | No
Cryptography | Region-scoped KMS with per-tenant keys and a documented rotation runbook (NFR-04) | Region-scoped encryption at rest | NB-283 | Must | Go-live blocker | No
Cryptography | TLS 1.3 only, HSTS preload, automated certificate renewal | Encryption in transit | NB-284 | Must | Go-live blocker | No
Cryptography | Column-level encryption for national identifiers | PHI field-level encryption | NB-285 | Must | Go-live blocker | No
Application | Parameterised queries and schema validation on every endpoint | Input validation & injection defence | NB-286 | Must | Go-live blocker | No
Application | OWASP Top 10 and API Top 10 pass, including IDOR/BOLA on patient and family-scoped routes | OWASP Top 10 & API Top 10 | NB-287 | Must | Go-live blocker | No
Application | Content Security Policy in enforce mode; no inline script | Security headers & frontend hardening | NB-291 | Must | Go-live blocker | No
Application | Uploads type-verified, AV-scanned and served only via signed short-lived URLs | File upload security pipeline | NB-292 | Must | Go-live blocker | No
Application | Rate limiting per IP, tenant, user and phone number, including the public aggregator number | Rate limiting, bot & abuse | NB-288 | Must | Go-live blocker | No
Messaging | A file is never sent into open chat — always an expiring, access-logged link (SYS-18) | Secure file delivery via expiring link | NB-076 | Must | Go-live blocker | No
Messaging | Number change or re-registration requires re-verification before any patient data is released | Messaging channel abuse | NB-289 | Must | Go-live blocker | No
Messaging | Fixed template text is uneditable in every send path, including the API | Variable-fill-only template enforcement | NB-191 | Must | Go-live blocker | No
Messaging | Consent gate on every outbound send, effective across all surfaces within one minute (SYS-02) | Consent gate on every outbound send | NB-196 | Must | Go-live blocker | No
Messaging | Child profiles can never receive marketing, enforced server-side (DPO-09 / CMP-04) | Child marketing block | NB-089 | Must | Go-live blocker | No
Messaging | India DLT registration complete; the surface is entirely absent for KSA tenants (CMP-07) | India DLT registration | NB-194 | Must | Go-live blocker in India | No
Supply chain | SCA in CI, SBOM per release, patch SLA by severity, build fails on critical CVE | Secrets scanning & dependency | NB-290 | Must | Go-live blocker | No
Detection | SIEM alerting on auth failures, privilege change, support access and mass export | Security logging, SIEM | NB-293 | Must | Go-live blocker | No
Detection | Immutable append-only audit trail with before/after values (SYS-13) | Immutable audit trail service | NB-238 | Must | Go-live blocker | No
Detection | No PHI written to application logs — verified by an automated scanner | Observability — metrics | NB-304 | Must | Go-live blocker | No
Resilience | Encrypted backups with point-in-time recovery, never crossing a region boundary | Backup, retention & restore | NB-306 | Must | Go-live blocker | No
Resilience | Immutable backup copies and an isolated recovery environment for ransomware | Business continuity & ransomware | NB-296 | Must | Go-live blocker | No
Resilience | DR drill meeting RTO 4h / RPO 15 min in both regions | Disaster recovery — RTO/RPO | NB-307 | Must | Go-live blocker | No
Resilience | A third-party outage never blocks clinical or billing work | Graceful degradation for third-party | NB-330 | Should | Post-launch acceptable | No
Resilience | A sync backlog is treated as a clinic working offline, not as lost data (SYS-22 / NFR-12) | Offline queue, replay & sync banner | NB-328 | Must | Go-live blocker | No
Assurance | Annual CERT-In-empanelled VAPT for India, plus the annual tenant drill (NFR-09) | Annual CERT-In-empanelled VAPT | NB-294 | Must | Go-live blocker in India | No
Assurance | Independent penetration test covering the KSA stack | KSA penetration test | NB-295 | Must | Go-live blocker in KSA | No
Assurance | Threat model reviewed with mitigations tracked | Threat model & security architecture | NB-282 | Must | Go-live blocker | No
Assurance | Breach runbook with a completed tabletop exercise | Breach-notification runbook | NB-248 | Must | Go-live blocker | No
Assurance | Platform-side breach and incident operations console (DPO-03 / SSA-05) | Platform breach management operations | NB-249 | Must | Go-live blocker | No
Privacy — India | DPDP Act 2023 pack: consent, notice, rights, grievance officer, breach reporting | India DPDP Act 2023 | NB-253 | Must | Go-live blocker in India | No
Privacy — Saudi | PDPL / SDAIA pack: residency, controller obligations, cross-border rules, retention | Saudi PDPL & SDAIA | NB-254 | Must | Go-live blocker in KSA | No
Privacy | Consent versioned, withdrawable, and a hard gate with owner evidence (CMP-01 / CMP-02) | Consent as a hard gate | NB-241 | Must | Go-live blocker | No
Privacy | Consent and DPA registry with full version audit (DPO-01) | Consent registry & versioned audit | NB-242 | Must | Go-live blocker | No
Privacy | DSR engine with statutory timers and automatic closure letters (DPO-02) | DSR workflow engine | NB-244 | Must | Go-live blocker | No
Privacy | Regulator or owner export within 72 hours, 3-year retention (NFR-07) | Patient data export & erasure execution | NB-078 | Must | Go-live blocker | No
Privacy | Retention defaults active from day one with a pre-delete notice (CMP-05) | Retention auto-rules | NB-245 | Must | Go-live blocker | No
Privacy | Retention clocks per region with legal hold overriding erasure | Medical record retention & legal hold | NB-247 | Must | Go-live blocker | No
Privacy | Data classification standard applied to every table and log field | Data classification & handling standard | NB-255 | Must | Go-live blocker | No
Privacy | Plan plus signed digital DPA required before the tenant may hold patient data (CEO-17) | Digital DPA gate | NB-276 | Must | Go-live blocker | No
Payments | PCI-DSS SAQ-A scope: no card data touches Nabd servers | Payment gateway integration | NB-168 | Must | Go-live blocker | No
Payments | ZATCA e-invoicing passes the sandbox compliance validator | Saudi VAT & ZATCA | NB-164 | Must | Go-live blocker in KSA | No
Payments | GST and ZATCA output independently verified against worked examples | Tax & invoice correctness test pack | NB-322 | Must | Go-live blocker | No
Clinical safety | Allergy conflicts cannot be overridden without a documented reason (DERM-05) | Allergy hard-warning | NB-108 | Must | Go-live blocker | No
Clinical safety | Paediatric dosing derives from recorded weight via a named, versioned rule source (PED-05) | Weight-based paediatric dosing | NB-112 | Must | Go-live blocker | No
Clinical safety | Pregnancy and lactation warnings fire without the Gynaecology profile (GYN-03) | Pregnancy & lactation warnings | NB-113 | Must | Go-live blocker | No
Clinical safety | Signed clinical notes immutable; amendments append with reason and author | Clinical note amendment | NB-104 | Must | Go-live blocker | No
Clinical safety | A procedure cannot proceed without recorded consent (DOC-09) | Procedure consent capture & signature | NB-119 | Must | Go-live blocker | No
Clinical safety | Emergency phrases halt aggregator routing and show emergency guidance only (AGG-02) | Emergency phrase interception | NB-222 | Must | Go-live blocker for aggregator | No
Clinical safety | Hazard log reviewed and signed by a clinical safety officer | Clinical safety test cases | NB-321 | Must | Go-live blocker | No
Traceability | Every wireframe requirement identifier mapped to a delivered, tested task | Requirement traceability & coverage sign-off | NB-343 | Must | Go-live blocker | No
People | Security awareness and clinical data handling training completed by all staff | Staff security awareness & data handling | NB-348 | Should | Before pilot | No
Go-live gate | Blocking controls outstanding
Controls verified

## Risks
Delivery, security and clinical-safety risks
ID | Category | Risk | Impact (1-5) | Likelihood (1-5) | Score | Mitigation | Related Tasks | Owner
R-01 | Clinical safety | A prescribing, dosing or allergy defect reaches production and causes patient harm. | 5 | 3 |  | Clinical safety test suite and hazard log signed by a clinical safety officer; mandatory override reasons; validated dose rule source; staged pilot rollout. | NB-321, NB-108, NB-112 | Clinical Lead
R-02 | Clinical safety | The aggregator routes an emergency to a clinic instead of emergency services. | 5 | 2 |  | Emergency phrase interception in every supported language runs before any routing; Nabd never interprets symptoms; unmatched input goes to reception, not a guess. | NB-222, NB-223 | Clinical Lead
R-03 | Security | Cross-tenant or cross-region leakage breaches PDPL residency rules. | 5 | 3 |  | Isolation proven by PoC in sprint 1; region locked irreversibly at provisioning; region-scoped KMS; no cross-region replication; independent penetration test per region. | NB-002, NB-271, NB-295 | Security Lead
R-04 | Security | The public aggregator number becomes an attack and enumeration surface. | 4 | 3 |  | Per-number and per-IP rate limiting, re-verification on number change before any data release, and abuse monitoring from day one of the aggregator build. | NB-288, NB-289 | Security Lead
R-05 | Vendor | Meta rejects templates, throttles quality or delays WhatsApp onboarding, stalling the patient product. | 5 | 4 |  | Managed onboarding started in sprint 9 ahead of patient build; fleet quality monitoring; automatic SMS fallback; no clinical journey is ever blocked on messaging. | NB-188, NB-264, NB-193 | Integration Lead
R-06 | Compliance | ZATCA Phase-2 e-invoicing rejects invoices and blocks billing in Saudi Arabia. | 5 | 3 |  | Build against the ZATCA sandbox from sprint 12; validate with the official compliance tool; independent tax test pack; manual invoice fallback retained. | NB-164, NB-322 | Finance / Tech Lead
R-07 | Compliance | India GST treatment of clinical services is misapplied, creating tax exposure. | 4 | 3 |  | Independent tax review of the GST engine; effective-dated rate tables; worked-example test pack reproduced to the paisa. | NB-163, NB-322 | Finance Lead
R-08 | Compliance | India DLT registration delays block all messaging to Indian patients. | 4 | 4 |  | Start DLT registration in parallel with the messaging build in sprint 13; keep templates minimal and stable; SMS fallback also requires DLT, so treat it as a single critical path. | NB-194 | Integration Lead
R-09 | Delivery | Scope is roughly double v1 and cannot be absorbed by a single team. | 5 | 4 |  | Four explicit delivery tracks; squad ramp published on the Sprints tab peaking at five squads; Phase 2 and Phase 3 items are separately funded and can be cut without touching MVP. | NB-343 | Delivery Manager
R-10 | Delivery | Nine clinical specialties are treated as one workstream and swamp the clinical track. | 4 | 4 |  | Specialty profile framework first, then one specialty at a time behind an entitlement flag; ENT, Ayurveda and Homeopathy are Phase 2 and droppable. | NB-121, NB-122 | Product Owner
R-11 | Delivery | RBAC complexity — twelve roles across clinic and platform — is underestimated. | 4 | 4 |  | Permission model built in sprint 4 before feature work; automated role-by-endpoint negative-test suite covering all twelve roles from sprint 12. | NB-049, NB-257, NB-317 | Tech Lead
R-12 | Product | The patient WhatsApp journey exceeds its tap budget and patients abandon booking. | 4 | 3 |  | Tap budgets are asserted automatically in the conversation test harness, not reviewed by eye; single-member numbers never see a picker. | NB-202, NB-316 | Product Owner
R-13 | Product | Family and proxy handling leaks one member's data to another. | 5 | 3 |  | Consent captured per member; proxy scope explicit and revocable immediately; wrong-family-member added to the clinical hazard log; IDOR testing covers family-scoped routes. | NB-081, NB-085, NB-321 | Security Lead
R-14 | Localisation | Arabic RTL, Hijri and anatomy-mirroring defects are found late because testing is English-first. | 3 | 4 |  | Pseudo-locale from sprint 3; RTL visual regression in CI including anatomy and chart time axes; native clinician sign-off on clinical strings. | NB-031, NB-319, NB-038 | QA Lead
R-15 | Operations | Clinic connectivity is poor and staff believe queued work has been lost. | 4 | 4 |  | Offline queue with ordered replay; sync banner states queued counts; platform health reports a backlog as offline working, not data loss; no destructive action offered while queued. | NB-328, NB-263 | Frontend Lead
R-16 | Operations | Morning-rush clinic load plus unbounded patient messaging concurrency degrades the queue. | 4 | 3 |  | Load test to twice expected peak on both sides; read-model separation for reports; provider backpressure rather than message loss. | NB-327, NB-331, NB-228 | Platform Lead
R-17 | Adoption | Reception reverts to paper because checkout is slower than their current process. | 4 | 3 |  | Time-on-task testing during UAT; keyboard-first checkout; command palette; pilot feedback loop in both regions. | NB-323, NB-162 | Product Owner
R-18 | Data | Legacy migration produces duplicate or mismatched patient records. | 4 | 3 |  | Dry-run imports with a validation report before any write; supervised merge with a 30-day reversal window. | NB-342, NB-072 | Data Lead
R-19 | Commercial | Self-serve trials create tenants holding patient data without a signed DPA. | 4 | 2 |  | The digital DPA gate blocks patient data entry until a plan is chosen and the DPA signed and versioned in the consent registry. | NB-276, NB-275 | Compliance / DPO
R-20 | Vendor | Payment gateway, lab or growth-service partners change their API mid-build. | 3 | 3 |  | An anti-corruption layer per integration; mock harness in CI; contract tests against provider sandboxes; growth percentiles deliberately delegated to a validated service. | NB-168, NB-132 | Integration Lead
Score = Impact x Likelihood. 15 and above is red and needs an active mitigation owner reporting weekly.

## Changes from v1
What changed when the wireframe was updated
v1 (11 Aug): 202 tasks / 1,210 points. v2 (13 Aug): 349 tasks / 2,260 points.
Change | Type | Detail | Impact
Requirement register introduced | Added | The wireframe now carries 185 formal requirement identifiers across 30 prefixes. Every task is traced to them and the Requirement Coverage tab proves complete coverage. | New traceability tab; a Requirement IDs column on every task
Patient WhatsApp surface | Added | PAT-01 to PAT-26. The patient product is a WhatsApp conversation, not a web portal — registration, booking, queue, payments, documents, privacy and language all in chat. | New epic E18, 20 tasks, 128 points
Caregiver, family & guardianship | Added | CGV-01 to CGV-10. One number for a whole family, proxy booking, dual delivery, revocation, age-18 handover and family plans. | New epic E09, 10 tasks, 65 points
Aggregator & demand layer | Added | AGG-01 to AGG-05. A shared Nabd number with invisible routing, emergency interception, word-to-specialty matching and verified-visit ratings. | New epic E19, 7 tasks, 56 points
Platform console rebuilt | Expanded | Seven segregated SaaS operator roles, provisioning as a resumable job queue rather than a wizard, subscriptions and dunning, discount approvals, support tickets with SLA, platform health and territories. | E22 grew from 10 tasks to 18
Chart & data-visualisation system | Added | DESIGN.md 8.22-8.29: an eight-slot series palette, all-pairs colour gate, inline SVG only, ten mandatory chart states and a table view for every chart. | New epic E03, 8 tasks, 49 points
Messaging component set & infrastructure | Added | DESIGN.md 8.16-8.21 plus managed WhatsApp onboarding, template governance, 24-hour session windows, delivery states, SMS fallback and India DLT. | New epic E17, 13 tasks, 100 points
Pharmacy properly specified | Expanded | PHR-01 to PHR-12 with three modes (external, hybrid, in-house), FEFO batch handling, controlled-drug register, refills and adherence capture. | Was one deferred task in v1; now epic E16 with 11 tasks
Compliance & data protection deepened | Expanded | CMP-01 to CMP-12 and DPO-01 to DPO-09: consent template library, consent as a hard gate, DSR engine with statutory timers, retention engine, breach ops, licence tracker and child-data controls. | E21 grew from 8 tasks to 19
Specialty workspaces broken out | Expanded | Nine specialties now specified individually: Dental (FDI storage, radiographs, staging, orthodontics, per-tooth timeline), Dermatology, Paediatrics, General practice, Orthopaedics, Gynaecology, ENT, Ayurveda and Homeopathy. | Was one 13-point task; now epic E12 with 21 tasks
Clinic setup & administration | Added | CAD-01 to CAD-13: a skippable, resumable, fully self-serve setup wizard, price master, policy settings, shift timings and self-serve import/export. | New epic E07, 11 tasks
Trial, sales & growth | Added | SCS-01 to SCS-04 plus the digital DPA gate — self-serve trial creation, inside sales, activation tracking and white-glove setup. | New epic E23, 7 tasks
SSO and hardware keys | REMOVED | NFR-06 states plainly: no SSO, no hardware keys. Staff sign in with WhatsApp OTP, a short PIN or an authenticator app. The v1 SSO/OIDC task has been deleted, not deferred. | v1 task removed; 8 points returned
Patient web portal (OTP) | REPLACED | v1 assumed an OTP web portal for patients. The wireframe replaces it entirely with the WhatsApp surface. | v1 task replaced by epic E18
Insurance claims scope narrowed | Re-scoped | SYS-10 makes full claims a Phase 3 certified-middleware integration and puts Ayushman out of scope. Only a simple claim export (BIL-11) and NPHIES eligibility-check-lite (RCP-07) remain in scope. | v1 groundwork task re-scoped into two bounded tasks
Payroll | Re-scoped | CAD-10 states there is deliberately no payroll engine — a CSV export only. | Bounded to a 5-point export task
Region residency hardened | Expanded | Region is now locked irreversibly at provisioning with region-scoped KMS keys and no cross-region replication (SYS-14 / NFR-04), rather than routing alone. | Isolation and KMS tasks strengthened; new security controls
Penetration testing split by region | Changed | NFR-09 requires an annual CERT-In-empanelled VAPT for India specifically, plus an annual drill with tenants. KSA needs its own independent test. | One v1 pentest task became two
Waiting-room display hardened | Expanded | RCP-14 adds liveness: paired, stale and connection-lost states re-checked every three seconds, and a TV scale that is explicitly not a breakpoint. | One v1 task became three
Consent moved into the data path | Changed | NFR-08 requires consent to be checked at query level, not in the UI. This is an architectural constraint, not a screen. | New foundational task in E06
Prayer-window send reconciliation | Added | SYS-03: routine sends defer around prayer windows, but operationally urgent broadcasts such as a doctor delay are not held. | New tasks in E04, E10 and E17
Anatomy excluded from RTL mirroring | Added | The dental arch and dermatology body map keep fixed left-to-right order in Arabic because they represent the patient's actual left and right. | Added to the RTL exception and test tasks
Delivery phase column added | Added | The wireframe marks items MVP, Phase 2 or Phase 3. That marking is now a data column so Phase 2 and 3 can be cut or funded separately. | 293 MVP / 50 Phase 2 / 6 Phase 3
Delivery model changed | Changed | v1 assumed a single 8-9 person team over 18 sprints. v2 needs four parallel tracks ramping to five squads (roughly 30 people) across 23 sprints. | New Tracks tab; squad ramp on the Sprints tab